04/22/2011

AMENDMENT #0002

STATEMENT OF WORK

National Environmental Policy Act Support for Pacific Southwest Region’s Comprehensive Conservation Plans

*************************************************************************************************

DELIVERY ORDER UNDER GSA FEDERAL SUPPLY SCHEDULE 899 (ENVIRONMENTAL SERVICES)

************************************************************************************************

- INSTRUCTIONS FOR RESPONDING TO THIS REQUEST FOR QUOTE

This statement of work describes the services the U.S. Fish and Wildlife Service’s (Service) needs to complete comprehensive conservation plans for national wildlife refuges in California.

This solicitation requests a firm-fixed price proposal that provides the services outlined in this statement of work.  The firm-fixed price proposal shall include:

- a table itemizes the full cost (labor, travel, other expenses, overhead, etc.) associated with each of the base and optional services described within the scope of work;

- a concise project plan (5 pages maximum) for performing the tasks; and

- a brief summary (2 pages maximum) of the Offeror’s qualifications and experience performing similar tasks in the statement of work.

The Service will base the selection on the proposal that represents the best value to the Government considering the project plan, past performance, cost, and qualifications.

- SUMMARY OF REQUIRED PRODUCTS AND SERVICES

Under this task order, the Contractor shall assist in the preparation of portions of a Comprehensive Conservation Plan and environmental assessment (CCP/EA) for the San Luis National Wildlife Refuge (NWR), Merced NWR and the Grasslands Wildlife Management Area. At the Government's option, the Contractor shall provide the NEPA support services for the Hopper Mountain, Bitter Creek, and Blue Ridge NWRs CCP/EA.

- STUDY AREA

- Base Contract: San Luis National Wildlife Refuge (NWR), Merced NWR and the Grasslands Wildlife Management Area. These refuge lands are part of the San Luis NWR Complex (SLNWRC).  SLNWRC consists of four refuges located in California's northern San Joaquin Valley:  San Luis, Merced, and San Joaquin River National Wildlife Refuges and the Grasslands Wildlife Management Area.  The area of analysis in the CCP/EA and this contract includes all refuge lands in the complex except San Joaquin River NWR, which is addressed under a separate planning process which has already been completed.  San Joaquin River NWR is not a part of this contract.

  - Background.  The San Luis and Merced NWRs and Grasslands WMA are in Merced County, California, adjacent to the communities of Los Banos and Merced.  They are situated within the San Joaquin River watershed in the San Joaquin Valley. Collectively, these three units of the National Wildlife Refuge System contain one of the largest remaining contiguous freshwater wetlands remaining in California, which provides important winter habitat for millions of migratory birds, as well as assemblages of other native wetland- and grassland-dependent wildlife.

  - The San Luis NWR was established in 1967 under the authority of the Migratory Bird Conservation Act and consists of 26,878 acres. The first parcel of the Refuge was purchased with Federal Duck Stamp funds to provide a sanctuary for migratory waterfowl. Since then, additional lands have been acquired. Today, the San Luis NWR includes six contiguous units: San Luis, Kesterson, West Bear Creek, East Bear Creek, Freitas, and Blue Goose.

  - The Merced NWR was established in 1951 under the authority of the Lea Act and Migratory Bird Conservation Act and consists of 10,262 acres. Under the Lea Act, a founding purpose of the Refuge was to attract waterfowl away from adjacent agricultural land where major crop depredation was occurring. In the last few decades, changes in local agricultural practices and Refuge management activities have reduced these wildlife/crop issues. The Refuge consists of the Merced, Lonetree, Arena Plains, and Snobird units.

  - The Grasslands WMA was established in 1979 under the authority of the Migratory Bird Conservation Act, Endangered Species Act, and Emergency Wetlands Resources Act. The Grasslands WMA includes approximately 190 properties under Service conservation easements (on private lands) totaling approximately 90,000 acres, within an approved acquisition boundary of 230,000 acres.

  - More information on the San Luis NWRC can be found on the internet at:  http://www.fws.gov/sanluis.

- Optional Element:  Hopper Mountain National Wildlife Refuge (NWR), Bitter Creek NWR and Blue Ridge NWR. These refuges are 3 of 4 refuges that comprise the Hopper Mountain NWR Complex (HMNWRC) in southern California.  The 4th refuge, Guadalupe-Nipomo Dunes NWR is not a part of this statement of work.

  - Background.  The Hopper Mountain NWR Complex was created primarily to restore the endangered California condor population to its native range.  Three refuges in the Complex (Hopper Mountain, Bitter Creek, and Blue Ridge NWRs) exist expressly for this purpose.

  - Hopper Mountain NWR is in Ventura County, approximately 6 miles north of the community of Fillmore. Hopper Mountain NWR was established in 1974 and encompasses 2,471 contiguous acres.

  - Bitter Creek NWR is located approximately 80 miles north of Los Angeles and approximately 10 miles southwest of the community of Maricopa in the arid foothills, primarily in Kern County.  The approved Refuge boundary includes lands in portions of Kern, Ventura, and San Luis Obispo Counties. Bitter Creek NWR is situated in the northern reaches of the Transverse Range, an ecologically diverse area where the Coast Ranges, Sierra Nevada Mountains, western Mojave Desert, and the San Joaquin Valley converge.  Bitter Creek NWR was established in 1985 and encompasses nearly 14,097 acres.

  - Blue Ridge NWR is located in central Tulare County in the foothills of the Sierra Nevada Mountains, 11 miles north of Springville and 17.5 miles northeast of Porterville, California.  Blue Ridge NWR was established in 1982 as a refuge in the Kern NWR Complex.  In 2000, Kern NWR Complex transferred the management of the refuge to Hopper Mountain NWR Complex.  Blue Ridge NWR encompasses 897 acres.

  - Key Issues at the Hopper Mountain Complex include:

- Manage for recovery of the California condor

- Grassland/upland management

- Native upland management/restoration

- Manage for endemic wildlife/plant communities

- Monitoring of key wildlife/communities

- Habitat fragmentation/connectivity

- Management of Threatened and Endangered species

- Invasive species management

- Riparian management (natural springs/seeps)/restored hydrology

- Public use opportunities/limitations

- Oil extraction activities at Hopper Mountain NWR

- DEFINITIONS  - None

- SCOPE

  - BASE TASKS

  - Initial Project Coordination. The Contractor shall assign a Project Planner within seven (7) days of the Notice to Proceed.  All tasks will be completed with oversight from the Refuge Planner.  Within seven (7) days of the Notice to Proceed, the Project Planner shall coordinate via telephone with the Refuge Planner to discuss the project schedule and to arrange to receive those materials necessary to allow the Project Planner to develop a basic understanding of the NWRC and the CCP process.

A planning initiation meeting will be held in Sacramento, CA within 3 weeks after contract award.  The purpose of the initiation meeting is to clarify the project outcomes; to discuss the overall planning process; to acquaint the Contractor with the Refuges and their purposes; to answer questions about the management alternatives to be analyzed in the Draft EA; and to provide other relevant information needed to complete the environmental consequences sections of the Draft EA.  Through review of materials provided by the Refuge Planner, the Contractor shall have developed a basic understanding of the Refuge, the CCP process, and management alternatives prior to the planning initiation meeting and should be ready to discuss CCP and EA.

  - Prepare the Environmental Consequences Section.  The Contractor shall analyze the environmental consequences of implementing each alternative in relation to the No Action Alternative, which serves as a baseline.  A methodology section which describes assumptions and how the analysis was conducted shall be included.  The Contractor shall also include a significance criteria section quantifying the threshold for significance of effects.  The sequence and format of environmental consequences (analysis of effects) to resources shall coincide with the sequence and list of resources in the Affected Environment chapter.  The list of resources will be furnished by the Government.  The Contractor shall include discussion of direct, indirect, secondary, and cumulative effects, as required by NEPA.  For each resource, the overall significance or insignificance of the impact shall be identified, with justification for its significance or lack thereof, with appropriate references.

The environmental consequences section should include an economic analysis which answers the following questions:

- What contribution does/would Refuge administration make to the regional economy?

- What is the value of Refuge administration and expenditures, expressed as $/acre?

- What does/would the Refuge public use program contribute to the region in overall economic output, employment, and employee compensation?

Use of graphics, charts, and maps clearly displaying the extent and relative magnitude of impacts is encouraged.  The format of deliverables shall fully comply with the draft planning Chapter of the FWS Manual.  The Contractor shall provide a reference list (literature cited section to support all technical citations in the EA).  The Contractor shall summarize the environmental effects of each alternative in a table.

The Contractor shall submit a draft environmental consequences section and reference list to the Refuge Planner for review within 45 calendar days of the Notice to Proceed.

The Government shall provide an alternatives figure (map) depicting the study area with a comparative graphic representation of each of the alternatives analyzed in the EA.

  - Layout, Format, and Edit the Draft CCP and EA.  The Contractor shall complete the following tasks in preparing the Draft CCP and EA:

    - Administrative Draft CCP and EA.  Within 60 calendar days of the Notice to Proceed, the Contractor shall submit:

- Ten (10) paper copies (3-ring binders) of the administrative Draft CCP, EA, and appendices; and

- One (1) CD-ROM containing the administrative draft documents in Adobe Acrobat (PDF) format suitable for printing or copying.

The documents shall be assembled from the information gathered under the previous tasks, plus the additional sections provided by the Refuge Planner. Compatibility determinations and any step-down plans will also be prepared by the Refuge staff for inclusion in the appendices.  The Contractor shall be responsible for editing and formatting all sections of the Draft CCP and EA and appendices.

The CCP will also include photos, maps, and other graphics, which will be prepared by the Refuge Planner and provided to the Contractor for inclusion in the draft documents.   The CCP format shall comply with the draft planning chapter of the Service Manual and Service’s graphic standards.  The Service estimates that its core planning team will provide review comments to the Contractor within 30 calendar days of receipt of the Contractor's submittal.  The Refuge Planner will collate the comments and identify and resolve any conflicts needing resolution by the core planning team prior to providing the comments to the Contractor.  At this phase, minor changes to the alternatives may be made by the Service.

    - Final Draft Public Review CCP and EA.  The Contractor shall incorporate all Service review comments and changes from the last submittal, in coordination with the Refuge Planner, to prepare a Final Draft Public Review CCP, EA and appendices.

Within 30 days after receiving comments on the administrative draft, the Contractor shall submit:

- one (1) camera ready master of the complete Draft CCP, EA, and appendices;

- one (1) CD-ROM containing copies of the Draft CCP, EA, and appendices in Adobe Acrobat (PDF) format suitable for printing; and

- one (1) CD-ROM containing copies of the Draft CCP, EA, and appendices in Adobe Acrobat (PDF) format suitable for reproducing and distributing to the public, and  for posting on a web site (this version should be indexed and searchable for ease of use by the public).

All deliverables shall be submitted to the Refuge Planner.

  - Respond to Public Comments.  Within 30 calendar days of the close of the public review and comment period, the Contractor shall provide draft written responses to all comments received from the public on the Draft CCP and EA.  The Service estimates that up to 25 public comment letters will be received on the Draft CCP and EA with up to ten comments per letter.  The Contractor shall prepare draft responses in coordination with the Refuge Planner.  The Contractor’s draft responses shall resolve or technically refute all substantive comments received.  The Service will provide comments on the Contractor’s draft responses to the Contractor within approximately 30 calendar days of receipt of the Contractor's submittal. Review comments will be coordinated by the Refuge Planner.  Based on the Service’s review comments, the Contractor shall revise the Draft CCP and EA comment responses.  The Service estimates that resolution of any issues or conflicts that arise from the review of draft responses can be achieved through a two-hour meeting or conference call between the Contractor and the Service.

  - Prepare Final CCP.  The Contractor shall complete the following tasks in preparing the Final CCP and EA:

    - Prepare the Administrative Final CCP and EA.  Within 30 calendar days after receipt of final comments on the response to comments, the Contractor shall submit an administrative Final CCP and appendices to the core planning team for review.  The submittal shall include:

- one (1) electronic version (Word or compatible format) and

- ten (10) hard copies (in 3-ring binders).

This administrative Final CCP shall include the Final EA, FONSI, response to comments, and address comments provided by the Refuge Planner.  The Service estimates that they will provide review comments to the Contractor within 30 calendar days of receipt of the Contractor's submittal.  The Service’s comments will be coordinated through the Refuge Planner, who will collate comments received on the administrative Final CCP and provide them to the Contractor for incorporation into the Final CCP.  Comments are expected to be limited to issues that can be resolved over the telephone and no meetings are anticipated for preparation of the administrative Final CCP.

    - Prepare Final CCP and EA.  Within 30 calendar days after receipt of the Service review comments, the Contractor shall submit the Final CCP and EA incorporating all review comments.  The Contractor shall submit:

- one (1) camera ready master of the document;

- five (5) paper copies (3-ring binders) of the Final CCP and EA (including appendices);

- one (1) CD-ROM containing the final documents in Adobe Acrobat (PDF) format suitable for printing; and

- one (1) CD-ROM of the Final CCP and EA and any appendices in Adobe Acrobat (PDF) format suitable for reproducing and distributing to the public, as well as posting on a web site (this version should be indexed and searchable for ease of use by the public).

All deliverables shall be submitted to the Refuge Planner.

  - OPTIONAL TASKS (Potential Future Component of this Task Order).

Funding is not currently available for these tasks, but may become available in the future.  Please provide a separate itemized quote for these task, do not incorporate the cost for these task into your overall quote to accomplish the other items included in this scope of work.

At the Government's option, the Contractor shall provide the NEPA support services for the Hopper Mountain, Bitter Creek, and Blue Ridge NWRs CCP/EA. These tasks include:

    - Initial Project Coordination.  Scope same as for the Base Task 1a.

    - Prepare the Environmental Consequences Section.  Scope same as for the Base Task 1b.

    - Administrative Draft Environmental Consequences.  The Service estimates that its core planning team will provide review comments to the Contractor within 30 calendar days of receipt of the Contractor's submittal. The Refuge Planner will collate the comments and identify and resolve any conflicts needing resolution by the core planning team prior to providing the comments to the Contractor.  At this phase, minor changes to the alternatives may be made by the Service.

Within 14 calendar days of receipt of review comments, the Contractor shall address and incorporate the review comments into the Environmental Consequences section of the Administrative Draft EA and submit:

- one (1) CD-ROM containing the administrative draft Environmental Consequences section in Word and Adobe Acrobat (PDF) formats suitable for printing or copying into the Administrative Draft EA.  At the discretion of the Refuge Planner, the deliverable may be submitted via electronic mail.

    - Respond to Public Comments.  Scope same as for the Base Task 1d.

    - Prepare Final EA.  The scope of work for this Optional Task shall be the same as Base Task 1e except the term “Final CCP and EA” or “Final CCP” shall be replaced with “Final EA” and as follows.

- PLACE/DELIVERY AND PERIOD OF PERFORMANCE

- No site visits are required.  The work shall be conducted at Contractor’s place of business.  The period of performance for this task order is May 2011 through December 1, 2012.

- INSPECTION AND ACCEPTANCE

- The deliverables shall generally follow the format and content specified in the draft planning chapter for the Service Manual and Service’s graphic standards. The documents shall be no longer than necessary to concisely address required contents, extensively use references to documents already in existence, describe which resources are eliminated from detailed analysis and why, focus on resources affected by the proposed action, and be written so that the layperson can understand the documents.  The use of technical jargon shall be minimized. Technical data shall be provided in appendices if needed for the reader's understanding, or shall be available from the Service if requested.  The Contractor is encouraged to submit products (or sections of products), as they are completed, to the Refuge Planner prior to the deadlines.

- GOVERNMENT FURNISHED EQUIPMENT OR MATERIALS/ INFORMATION

- The Government will:

- Provide overall project management for the CCP and EA process, as well as oversight and guidance to the Contractor on this project.

- Provide guided site visits to the study area.

- Provide all available data and reports related to geology, soils, water quality, topographic information, biological resources, current and past public use and visitor services, as well as any available visitor profile information (e.g., demographics, annual and peak visitation).

- Provide GIS data including approved refuge boundaries, ownership boundaries, vegetation communities, species distribution and other relevant data.

- Provide existing management plans, environmental compliance documents, and resource survey reports and text of the National Wildlife Refuge System Improvement Act of 1997 (P.L. 105-57).

- Provide photos, maps, and other graphics for inclusion in the draft documents.

- Prepare all planning updates (newsletters).

- Conduct public scoping.

- Prepare all required Federal Register Notices.

- Prepare the NEPA decision document

- Handle all printing requirements for public distribution documents through the Government Printing Office.

- Provide written descriptions of management alternatives for NWRC for inclusion into the CCP and environmental assessment.

- Provide the Contractor with a CCP and EA outline and all sections of the CCP and EA other than the environmental consequences.

- DELETED FROM SOW: Provide the Contractor with the list of resources (that shall be described by the Contractor in the Affected Environment chapter and analyzed by the Contractor in the Environmental Consequences chapter.

- Provide all required revisions to the preliminary draft and administrative draft CCP and EA and final CCP that are the result of comments provided by the core team, Regional Office, and/or the public that will be incorporated into subsequent documents by the Contractor.

- AVAILABILITY

No access to the refuges is required under this task order.

- TECHNICAL COORDINATORS

Base Tasks:

Mark Pelz, Chief

Refuge Planning

U.S. Fish and Wildlife Service

2800 Cottage Way, Room W-1832

Sacramento, CA 95825-1846

916-414-6504

916-414-6497 (fax)

mark_pelz@fws.gov

Optional Tasks:

Sandy Osborn, Refuge Planner

U.S. Fish and Wildlife Service

2800 Cottage Way, Room W-1832

Sacramento, CA 95825-1846

916-414-6503 (phone)

916-414-6497 (fax)

Sandy_Osborn@fws.gov