Statement of Work

Izembek National Wildlife Refuge, Alaska

Land Exchange

Environmental Impact Statement

I.  Introduction

The Department of the Interior, U.S. Fish and Wildlife Service (Service), Alaska Region requires contractor support services to prepare an Environmental Impact Statement (EIS). The EIS will analyze the impacts of a proposed land exchange between the Service, the State of Alaska, and the King Cove Corporation.  It will also evaluate the impacts of a road through the Izembek National Wildlife Refuge (Refuge) and the Izembek Wilderness Area.

In the Omnibus Public Land Management Act of 2009 (H.R. 146, Subtitle E; the Act), Congress directed the Service to prepare an EIS under the National Environmental Policy Act of 1969, as amended (42 U.S.C. 4321 et seq.) and its implementing regulations (40 CFR parts 1500-1508) to evaluate the impacts of a proposed land exchange with the State of Alaska and the King Cove Corporation for the purpose of constructing a single-lane gravel road between the communities of King Cove and Cold Bay, Alaska. The land exchange would involve the removal of approximately 206 acres within the Izembek Wilderness portion of Izembek National Wildlife Refuge for the road corridor and approximately 1,600 acres of Federal land within the Alaska Maritime National Wildlife Refuge on Sitkinak Island. In exchange, the Service would receive approximately 43,093 acres of land owned by the State of Alaska (to be designated wilderness) and approximately 13,300 acres of land owned by the King Cove Corporation. These lands are located around Cold Bay and adjacent to the North Creek Unit of Alaska Peninsula National Wildlife Refuge.

Izembek National Wildlife Refuge consists of 417,533 acres at the westernmost tip of the Alaska Peninsula.  The Refuge also manages the North Creek (8,452 acres) and Pavlof (1,447,264 acres) units of the Alaska Peninsula National Wildlife Refuge and Unimak Island (1,008,697-acre) of the Alaska Maritime National Wildlife Refuge. To the north of the Izembek Refuge is the Bering Sea; to the south is the Pacific Ocean. Birds from all over the Arctic funnel through Izembek Refuge each fall on their way to wintering grounds throughout the world. More than 98 percent of the world’s Pacific black brant use Izembek Lagoon as a staging area for their fall migration to Mexico. Other birds that use the refuge include golden plover, ruddy turnstone, western sandpiper, tundra swan, the federally threatened Steller’s eider, and emperor geese. The refuge is also home to large concentrations of brown bear and other large mammals such as caribou and wolf. The red, pink, chum, and silver salmon that use the waters within the refuge enrich the entire ecosystem with nutrients they bring from the sea. The Izembek Wilderness (300,000 acres) covers much of the refuge and includes pristine streams, extensive wetlands, steep mountains, tundra, and sand dunes.  It provides high scenic, wildlife, and scientific values, as well as outstanding opportunities for solitude and primitive recreation.

The King Cove Corporation is an Alaska Native Village Corporation established under the Alaska Native Claims Settlement Act of 1971 (ANCSA; 43 U.S.C. 1601 et seq.).  Per the authority of ANCSA, Congress granted to King Cove Corporation land entitlements within and adjacent to Izembek Refuge. The State of Alaska also owns lands, submerged lands, shorelands, and tidelands (including the Izembek State Game Refuge) within and adjacent to Izembek and Alaska Peninsula Refuges.

The Service will be leading a team of cooperators, including Army Corps of Engineers (ACOE), State of Alaska (Departments of Natural Resources, Fish and Game and Transportation and Public Facilities), Agdaagux Tribe, City of King Cove, Aleutians East Borough and the Alaska Migratory Bird Co-Management Council to complete the EIS. The Service is in the process of developing cooperative agreements with the respective parties.  The Contractor will be expected to work with the cooperators; however the Service will be the lead agency.

At this time, the Service anticipates that the Contractor will be hired during the public scoping process. Therefore, the Contractor will have the responsibility o analyzing and summarizing the comments from scoping.  The contractor will not participate in the scoping meetings.

The Contractor will prepare an EIS that is technically and legally defensible and in full compliance with the requirements of NEPA (42 U.S.C. 4321 et seq.); the Council on Environmental Quality Regulations (CEQ; 40 CFR §1500-1508); and the Service NEPA Handbook.  In addition, the Contractor shall comply with ACOE requirements for NEPA analysis.  The Contractor will analyze public scoping comments, initiate consultations, prepare draft environmental documents for internal Service and cooperating agency review, revise environmental documents in response to review comments, prepare the environmental documents for public review and comment (distribute CDs, upload to the web, and provide the printer with mailing labels and the appropriate digital files for printing), analyze public comments on the draft EIS, and prepare a final environmental document. The Contractor will perform all necessary technical analyses, edit the documents, prepare graphics, prepare camera-ready copies and provide electronic documents for public distribution and review. The Service will assume the costs of printing and mailing the Draft and Final EIS documents.

II. Scope

- Overview: The Contractor will develop an EIS with a comprehensive impact analysis that includes direct, indirect, and cumulative impacts for all resource issues and concerns. In accordance with Section 6402(b) (2) (B) of the Act, the EIS will analyze the proposed land exchange, and construction and operation of a road between the communities of King Cove and Cold Bay, Alaska.  It will evaluate a specific road corridor through the Izembek Refuge that will be identified in consultation with the cooperators, including State of Alaska, City of King Cove, Alaska, and the Agdaagux Tribe of King Cove. At a minimum, the alternatives anticipated at this time include the existing situation (no land exchange or road construction) and the proposed land exchange and road construction and operation as outlined in the Act.

- 1. Land exchange and Road Construction.  The land exchange would involve the removal of approximately 206 acres from the designated Izembek Wilderness portion of Izembek National Wildlife Refuge for the road corridor and approximately 1,600 acres of Federal land within the Alaska Maritime National Wildlife Refuge on Sitkinak Island. Those lands would be removed from the Federal estate.  In exchange, the Service would receive approximately 43,093 acres of land owned by the State of Alaska and approximately 13,300 acres of land owned by the King Cove Corporation, of which, 43,093 acres will be designated Wilderness. These lands are located around Cold Bay and adjacent to the North Creek Unit of Alaska Peninsula National Wildlife Refuge.

2. No action.  The Service would not enter into a land exchange with the State of Alaska and King Cove Corporation.   Therefore, the road as proposed would not be constructed.

C.	Analysis Issues:  During scoping, the public, non-governmental organizations (NGOs), Tribal organizations, and State/Federal/local governmental agencies will identify issues for analysis. Preliminary scoping identified several issues we believe will be important in the analysis.  These may include, but are not limited to the following:

1.  Refuge Purposes. The potential for conflicts with the purposes of the Refuge. Establishing legislation for the Izembek National Wildlife Refuge under Alaska National Interest Lands Conservation Act (ANILCA) identified several purposes for which the Refuge was established and shall be managed, including:

(i) to conserve fish and wildlife populations and habitats in their natural diversity; including, but not limited to, waterfowl, shorebirds, and other migratory birds, brown bears, and salmonoids;

(ii) to fulfill the international treaty obligations of the United States with respect to fish and wildlife and their habitats;

(iii) to provide, in a manner consistent with the purposes set forth in subparagraphs (i) and (ii) the opportunity for continued subsistence uses by local residents;

(iv) to ensure, to the maximum extent practicable and in a manner consistent with the purposes set forth in paragraph (i), water quality and necessary water quantity within the refuge.

Refuge Purposes under the National Wildlife Refuge System Administration Act of 1966, as amended by the National Wildlife Refuge System Improvement Act of 1997 (16 U.S.C. 668dd-668ee).

In addition to ANILCA purposes, the National Wildlife Refuge System Improvement Act of 1997 stated that wildlife observation, photography, interpretation, environmental education, hunting, and fishing will be considered as appropriate use on refuges.  Izembek refuge is used by many sport hunters for waterfowl hunting. Therefore, an analysis needs to be completed on recreational uses of the refuge both positive and negative.  Izembek Lagoon is a designated Wetland of International Significance by the RAMSAR organization.  The effects to the lagoon will need to be analyzed.

2.  Wilderness Designation.  The proposal for the land exchange will remove approximately 200 acres from the Izembek Wilderness and add approximately 43,000 acres to the Alaska Peninsula refuge that will be designated Wilderness.

3.  Environmental Impacts. The potential environmental effects to air, water (surface, groundwater, hydrology), threatened and endangered species, fish, wildlife, and plants and their habitats that may result from the construction, maintenance, and operation of a road to be analyzed.  Other potential effects to be analyzed include the disruption or alteration of migration or travel routes of animals (bear, caribou, furbearers, waterbirds, and upland birds), the displacement of species from their nesting, feeding, breeding, and roosting areas and effects on species distribution and vulnerability to hunting pressure or other human disturbances. Filling of wetlands and/or altering wetland hydrology and the affects those actions may have on fish, plants, habitat, bear, and waterfowl and waterbirds will be analyzed.

4.  Subsistence Impacts. The potential effects on subsistence resources and subsistence users;

5.  Insufficient Information. The potential that available biological, environmental, and socio-economic data may be insufficient to analyze the impacts of the exchange;

6.  Impacts to Rural Communities. The potential for both positive and negative impacts on rural communities within the Izembek refuge region, including an analysis of the community composition, long term cultural use, demographics, land ownership, among others;

7.  Loss of Native-owned Lands. The opposition to the divestiture of Native lands within the Izembek refuge region;

8.  Socio-economic Impacts. The potential for direct and indirect positive and negative effects on the cultural, social, and economic well being of local communities;

9.  Public Use.  An analysis of the current baseline of public use on refuge lands and adjacent properties, including current trails and roads, and the potential for increased use of the lands with the proposed road development;

10.  Refuge Benefits. The potential to increase the amount of land protected by Refuge ownership and facilitate management by consolidating both Refuge and private ownerships. Conduct an analysis of the quality of lands being exchanged.

11.  Cultural Resources.  The potential for the disturbance or removal of cultural resource or any other impact the contractor may find during this assessment.

12.  Climate Change.  Identify the relationship of the effects of the project on a changing climate.

13.  Public Interest.  The Secretary of the Interior “shall determine that the land exchange, including the construction of a road between the City of King Cove, Alaska, and the Cold Bay airport is in the public interest”.

D. Analysis Factors:  Relevant resources, current and potential land uses, and potential positive and negative impacts should be described at a level of detail that will enable decision-makers to make informed choices.

E. Statutory, Departmental, and Agency Guidance: The Contractor shall write the EIS and follow the requirements of NEPA CEQ regulations at 40 CFR 1500 – 1508, Departmental Manual (DM) Part 516 DM 1, 2 and 4, and guidance in the Service NEPA Reference Handbook. In addition, the Contractor shall follow the appropriate guidelines from the ACOE.  The Service Printing and Publishing Manual Part 121 AM, the Chicago Manual of Style, and the Shipley Associates Style Guide will be the publication and style standards. The Contractor must meet all legal and policy requirements regarding public notices, required elements, distribution of draft and final documents, and other applicable laws. The Contractor will ensure the EIS process is in compliance with the Federal Advisory Committee Act (FACA) when soliciting input and comment from advisory committees, industry, and/or other nongovernmental organizations. Appendix A lists some relevant statutory, Departmental, and Agency guidance.

F. General Guidance: The EIS process will adhere to CEQ regulations by following these guiding principles:

  - Descriptions of the affected environment will be no longer than necessary to understand the impacts of the alternatives (40 CFR 1502.15).

  - The EIS will present the environmental impacts of the alternatives in comparative form, sharply defining the issues and providing a clear basis for choice among options (40 CFR 1502.14). The analysis will lead to incisive conclusions about the amount and degree of change (impact) caused by the proposed action and alternatives.

  - The length of the EIS will be minimized by incorporating materials by reference (40 CFR 1502.7; 1502.21).

  - The EIS will focus on significant issues rather than amassing needless detail (40 CFR 1500.01).

  - The EIS will be written in plain language (40 CFR 1502.8).

  - The EIS writers will reduce paperwork and extraneous background data and emphasize real environmental issues and alternatives (40 CFR 1502.1; 1502.7).

  - The EIS will be clear, concise, to the point, and supported by evidence that the Service has made the necessary environmental analyses (40 CFR 1500.2).

G. Geospatial Datasets: The EIS team will use Geographic Information Systems (GIS) technology to model existing conditions and to predict the effects of alternatives on the landscape. In addition, GIS will be used to create figures and/or maps displaying the results of the analyses. The Contractor will upload some of these figures and/or maps (determined in conjunction with the Service) to the internet for public access during comment periods.

Several useful data sets are available through the Fish and Wildlife Service Regional Office, Division of Realty, and the Izembek National Wildlife Refuge. The Service is in the process of acquiring High Resolution satellite imagery for the area to be used in the Izembek EIS.  However, the Contractor may need to acquire additional data. State, Tribal, and local governments and NGOs are potential sources of GIS data. It is important to avoid compiling more GIS and other data than required to analyze impacts and make informed decisions. All newly acquired data will conform to the appropriate Service standard, or to documented data standards of other cooperating agencies or entities. Data should be developed and documented in a manner to encourage data sharing between partnerships involved in the EIS.

H. Public Participation:  The public, industry, NGOs, other Federal agencies, and Tribal, State, and local governments must have opportunities to comment and participate in the EIS process. The Service will make every effort to ensure that attitudes, beliefs, needs, and concerns of local, regional, and national interests are considered when making land use decisions. To comply with Executive Order 13175, the Service will actively consult with Tribes that are substantially and directly affected by actions the agency is contemplating. The Contractor will have the responsibility of assisting in public outreach, including producing planning updates or flyers; furnishing materials for a well-maintained, up-to-date, and informative website; coordinating, providing logistical support, and participating in public and Tribal meetings; and documenting, analyzing, and summarizing the results of the public participation activities and Tribal consultation.

III. Government-Furnished Materials

The Service will provide:

- Mailing List: The Service will provide the Contractor with a preliminary mailing list for the project. The Contractor will be responsible for updating and maintaining the mailing list and providing the updated list when required for document distribution.  This mailing list will be property of the Service.

- Species Lists/Biological Information Collected by the Service:  The Service will supply a list of plants and animals known to occur in the project area and other pertinent biological information previously collected by the Service.

- Contracting Officer Representative (COR):  The Service will provide a designated Project Coordinator, who will serve as COR and liaison between the Contractor and the Service.

D.	Service Staff:  The Service will provide two or more representatives at all public scoping meetings, workshops, or hearings.

E.	Reference Materials:  The Service will provide relevant reports and studies, guidelines, manuals, handbooks, examples, publication standards, printing standards, mapping standards, or references to readily available copies of such documents. The Service will provide H.R. 146 Subtitle E – Izembek National Wildlife Refuge Land Exchange and text for the ANILCA 810 analysis. Appendix A includes some useful references to guidance documents.

F.	Geographical Information System Products:  The Service will furnish available GIS layers, maps and other GIS data for the Contractor’s use in developing document maps, graphics, and resource impact analysis. The Contractor may need to acquire additional GIS data from other sources.  ArcInfo or Arc GIS will be the GIS software used.

G.	Federal Register Notices:  The Service will prepare and issue all Federal Register Notices of Intent and Availability and associated documents for the EIS.

H.	Scoping Comments:  The Service will furnish the Contractor with scoping comments received prior to issuing the contract.   The comments will be provided in various formats, including lotus notes archive from email, hard copy, and electronic copy in formats received, including both Word and PDF.  In addition, the Service will provide the Contractor with public scoping notes and transcripts in Word 2003 or 2007.

I.  Printed Copies of Draft and Final EIS:  The Service will assume the costs of printing and distributing the Draft and Final EIS using a Government Printing Office (GPO) print contract. The Contractor will provide the Service will digital files, ready for printing and addressing.

V.  Tasks of the Contractor

The Contractor will furnish all personnel, equipment, supervision, supplies, and incidentals except those indicated as government-furnished, to perform all work necessary to complete the EIS in accordance with the Contract and task orders issued. The Contractor will be responsible for transportation costs/arrangements for essential Contractor staff to attend Draft EIS meetings/hearings in Washington DC, Anchorage, King Cove, Cold Bay, Sand Point and Nelson Lagoon.

The Contractor’s Project Manager will be available to the COR during normal business hours. During some stages of the project the Contractor’s Project Manager and some staff will have to be available for more extended hours. All phases of the contract will require frequent meetings (some involving the entire inter-disciplinary team) and phone and electronic mail contacts between the Contractor staff and Service staff.

The EIS must be legally defensible and meet the requirements of applicable laws, regulations, court decisions, and manuals. Specifically, the Contractor must perform the following tasks:

NOTE:  Implementation phases and tasks are dependent upon the availability of funding. Phases 1 and 2 are scheduled for fiscal year 2010/2011 and Phases 3 and 4 for fiscal year 2011/2012. Tasks 7 and 8 of Phase 1 (establishing a website and the administrative record) will continue throughout all phases. The estimated period of performance for the phases and tasks has been tentatively identified whenever possible.

Implementation Phases I-IV

Phase I

Phase I - Task 1: Project Work Plan

The EIS is expected to be completed by spring of 2012, with the goal of issuing the Record of Decision (ROD) by April 30, 2012. The EIS preparation will require an experienced interdisciplinary team with expertise in hydrology (ground and surface(wetlands, streams, lakes, & springs) waters) and hydrologic processes, threatened and endangered species, fish and wildlife biology (especially waterfowl, shorebirds, brown bear and caribou as well as resident and anadromous fish), wildlife corridors and migration patterns, conservation biology, landscape ecology, air quality, climate change, greenhouse gas emissions, ecology, terrestrial and aquatic plant communities, soils and geology, environmental contaminants (air, water, soil, and food chain), noise, light, and the effects to wildlife, impacts to wetlands, subsistence, socio-economics, archeology, and cultural resources.

The Contractor should include in its proposal a preliminary work plan that outlines a strategy for completing all phases of work within a reasonable timeframe. The preliminary work plan should identify how the Contractor will achieve all tasks. At a minimum, it should identify the:

(1) work breakdown structure,

(2) risk management strategy,

(3) critical path schedule and a detailed schedule for all elements of EIS preparation (including internal and public review times),

(4) staffing plan (identify on-board skills/skill needs; identify Project Manager and Contractor team members; include CVs of key personnel),

(5) cost estimate breakdown; include an estimate of work hours per position (i.e. estimated work hours the biologists, geologists, Project Manager, social scientists, or other key personnel, including subcontractors, will devote to the project from beginning to end); and

(6) steps the Contractor will take to assure quality of each aspect of the EIS effort.

Tentative due dates for deliverables are outlined in this Statement of Work. The proposed due dates in the Contractor’s preliminary work plan may deviate from those presented here, provided the work plan presents a successful strategy for completing all phases of work within a reasonable timeframe, with the goal of issuing the ROD by April 30, 2012.

After contract award, the Service and the Contractor will refine the preliminary work plan developed for this proposal. The final work plan will include due dates for deliverables and for any Service-provided materials required to complete the task. All deliverables must be satisfactorily completed by the deadlines listed in the final work plan. The work plan will be used to track progress throughout the EIS process.

The Contractor will appoint a project management team that includes a Project Manager, Contractor team members, and Service team members. The Contractor will coordinate with the Service’s COR to identify Service contacts for Contractor team members. The Contractor will develop a protocol for submitting brief management reports to the COR. Working processes and protocols will be refined during preliminary coordination meetings with the Service. All phases of the contract will involve numerous meetings (some involving the entire inter-disciplinary team) and frequent phone and electronic mail contacts between the Contractor staff and the Service.

Tentative dates for some major milestones are:

| Phase I (FY10) | Work Plan 42 days post-award Consultation Strategies………………………………………….. May 28, 2010 Public Participation Plan 41 days post-award Public Scoping Report……………………………………………..June 30, 2010 Preliminary data/identify data gaps ………………………………June 30, 2010 Specialists’ Reports ………………………………………………..June 30, 2010 Create and Maintain an EIS Website…………from date of award through ROD Administrative Record.………..............................from date of NOI through ROD |
| --- | --- |
| Phase II (FY10/FY11) | Affected Environment ………………………………………………August 30, 2010 Alternatives section…………………………………………………August 30, 2010 Environmental Consequences/Effects Analysis……………...September 30,2010 Prepare and distribute internal review Draft EIS December 30, 2010 |
| Phase III (FY11) | Internal review DEIS………………………………………………January 31, 2011 Address internal review; prepare Draft EIS March 31, 2011 Solicit comments - DEIS/ANILCA 810 April 1, 2011 - June 30, 2011 Draft EIS public meetings/hearings…....................April 2011 through June 2011 Evaluate public comment and prepare report August 30, 2011 Prepare responses to comments……………………………September 30, 2011 |
| Phase IV (FY12) | Prepare internal review FEIS November 30, 2011 Internal review of FEIS…………………………………………December 30, 2011 Prepare FEIS ……………………………………………………February 28, 2012 Issue FEIS & waiting period ……………………………………February 28, 2012 Issued ROD, public interest finding …………………………………April 30, 2012 Administrative Record (final)...………............................................June 30, 2012 |

In compliance with the Service’s NEPA policy, the Draft EIS comment period must extend for a minimum of 90 calendar days after the Environmental Protection Agency (EPA) provides notice in the Federal Register of the DEIS’s availability. At least 30 days must elapse between releasing the Final EIS and signing the ROD. In addition to these legal timing requirements, the Contractor should allow three (3) weeks for printing the Draft EIS and Final EIS from the date the printer confirms the adequacy of the electronic files furnished by the Contractor.

The Contractor and the Service will agree on a comprehensive schedule in the approved final work plan. Completion dates for deliverables from the Contractor may be adjusted during the EIS process due to delays caused by prolonged government review and approval (when approval from higher levels of the Service or Department of Interior is required); public concern/controversy; meeting delays, particularly in bush Alaska, due to weather or unscheduled community events; and printing and publication delays. However, after the delaying issue is resolved, the Contractor must be prepared to quickly return resources to the EIS preparation.

Deliverable: Written Final Work Plan for implementing all phases.

Due dates: Draft Work Plan for implementing all phases is due twenty-one (21) calendar days after date of award. The Service will review within seven (7) calendar days of receipt. After receiving comments, the Contractor will submit the Final Work Plan to the Service within fourteen (14) calendar days. If the Service has no comments, deliverable will be accepted as final.

Phase I - Task 2:  Public Participation Plan

The Contractor will develop a Public Participation Plan that includes strategies for coordinating and communicating with the public, NGOs, and other Federal, Tribal, State, and local governments and agencies. The Public Participation Plan will include strategies to encourage public participation throughout the EIS process. In particular, the plan should pay close attention to the needs of local communities and Tribal organizations.

The strategies will include, but are not limited to: conducting public meetings with the use of posters and large maps, issuing news releases in coordination with the Service-External Affairs, mailings, newspaper notices, media announcements, updates, dissemination of information through a website, and other informal contacts. The Contractor is responsible for completely involving the public in the EIS process and for disseminating information pertaining to this project. The Contractor will conduct public meetings/hearings for the Draft EIS; at least two Service employees will be present at any public meeting/hearing. The Contractor will be responsible for planning and facilitating these meetings. The Service will provide a preliminary project mailing list. The Contractor will be responsible for maintaining and updating (adding names and addresses, revising/correcting addresses, deleting incorrect addresses, etc.) the mailing list throughout the EIS process. The Contractor will provide the Service with the updated mailing list at the Service’s request.  This mailing list remains property of the Service.

The Public Participation Plan will include a strategy for reviewing and analyzing public comments through a comment-response management system platform. The Service is anticipating approximately 100,000 comments on this EIS.  Therefore, the Contractor must have a strategy for handling and processing large volumes of comments, including many form letters sent by fax or email. The Contractor will be responsible for uploading documents to the web in HTML or PDF formats, as appropriate.

All external information will require Service approval prior to release. Inquiries from the media, general public, government officials, and others will be referred to the Service.

Deliverable: Final Public Participation Plan

Due dates:  Draft Public Participation Plan twenty-one (21) days after contract award. The Service will review within ten (10) calendar days of receipt. The Contractor will then provide the final Public Participation Plan to the Service within ten (10) calendar days. If the Service has no comments, deliverable will be accepted as final.

Phase I - Task 3: Consultation Strategies

Subtask 1:  In coordination with the Service, the Contractor will meet with the National Oceanic and Atmospheric Administration (NOAA)-Fisheries to develop an appropriate strategy to initiate and conduct Essential Fish Habitat (EFH) consultation. The Contractor will draft a letter (to be approved and signed by the Service) to NOAA-Fisheries initiating the process.

Subtask 2:  In coordination with the Service Archeologist, the Contractor will meet with Alaska’s State Historic Preservation Office to determine a strategy to initiate and conduct National Historic Preservation Act (NHPA) Section 106 consultation. The Contractor will draft a letter (to be approved and signed by the Service) to initiate consultation.

Subtask 3:  Coordinate with the Service Endangered Species/Marine Mammal Management office on threatened and endangered species that are found in the area.  The Contractor will draft a letter (to be approved and signed by the Service) initiating Section 7 consultation.

Subtask 4:  Coordinate with the State of Alaska on fish, wildlife, habitat, and state land use matter, including the impacts to the Kinzarof Lagoon as part of the Izembek State Game Refuge Management Plan.  In addition, coordinate with the State on a Coastal Zone Consistency Determination.

Subtask 5:  All field activities must be coordinated with the refuge manager of Izembek refuge prior to implementation and a Minimum Requirement Analysis for administrative activities on Wilderness lands will be documented through the Minimum Requirement Decision Guide.

Subtask 6: Through the Service representative, coordinate with the ACOE on the Clean Water Act Section 404(b) (1).  Guidelines, project purpose and need under Section 404, wetland delineation requirements, and the April 10, 2008, Final Mitigation Rule.

Deliverable:  Consultation letters

Due dates:  Subtasks 1-3:  Final consultation letters due May 28, 2010

Phase I - Task 4 Scoping Comment Report:

The Contractor will collect, organize, analyze, and summarize scoping comments from all seven (7) scoping meetings.  Comments will be received through multiple means, including meetings, the project website, facsimile, and mail. All products must be preapproved by the COR before distribution.

The Contractor will develop a comprehensive Scoping Report that details and summarizes the results of the scoping meetings and all comments. The Scoping Report will be the record of information and comments received from the public, Tribes, NGOs, and Federal, State and local agencies on issues, concerns, alternatives, and data and data sources. The Scoping Report will be the basis for identifying the issues regarding the alternatives, to be discussed in the EIS. The Scoping Report should incorporate comments from all sources.

The Contractor will develop concise public scoping updates that summarize comments received during the scoping period. The Contractor will submit an electronic version and up to five (5) paper copies of the update to the COR for internal review. The Contractor will incorporate internal comments, prepare the camera-ready copy and deliver one (1) copy to the COR for pre-print review and approval. The Contractor will print and distribute up to 3,000 updates to individuals, agencies and organizations on the mailing list. The Contractor will upload the update to the project website.

Deliverables:  Scoping report and public scoping update that summarizes comments received during the scoping period.

Due date:   Scoping Report with comments collated and analyzed is due June 30, 2010.

Phase I - Task 5:  Preliminary Data/Data Gaps Briefing

The Contractor will review available literature, including literature in refuge files, on the affected resources and uses (subsistence, recreational, etc), consider data and data gaps identified in scoping, consult with the Service, and specialists from universities, the private sector, other Federal and State agencies and tribal and local governments. The Contractor will prepare an annotated bibliography of all reference materials evaluated in preparation of the EIS. The Contractor will present (to the planning team) an informal briefing/presentation summarizing the existing data relevant to a comprehensive impact analysis that will address the issues identified in scoping. The presentation should identify major relevant resources and uses; the interrelationship of these resources and current uses both with each other and with potential new developments; major sources of existing information; and additional information that would be useful, how it might be used in our impact analysis and decision making, and potential sources of the additional information.

Deliverable:  Briefing/presentation.

Due date:  June 30, 2010

Phase I - Task 6: Specialists’ Reports

The Contractor will prepare reports on the resources and uses to be analyzed in the EIS. At a minimum, these reports will:  1) describe the resources/uses in sufficient depth and in a format that will be easily incorporated into the Affected Environment chapter of the EIS, 2) include relevant maps and GIS data, 3) list literature cited, and 4) identify opportunities to improve the analysis of impacts by accessing data not yet reviewed or available.

Deliverable: Specialists’ Reports

Due date:  June 30, 2010

#### Phase I – Task 7: Create and Maintain an EIS Website

The Contractor will create and maintain a website dedicated to the EIS. It will contain up-to-date information about the EIS process and schedule and will provide access to important documents relevant to the EIS, including, but not limited to, the Draft and Final EIS, updates, news releases, and Federal Register notices. It will be linked to the Service’s website. The website will be easy to navigate to obtain desired information. During comment periods, the website will offer an electronic comment form for the comment period on the Draft EIS. Using this method of capturing public comment will facilitate reviewing and responding to comments.

Deliverables:  Create and maintain a website with appropriate links to the Service website. Upload updated information and comment forms for scoping comments and Draft EIS comments.

Due dates:  Establish the website, approved by the Service, within fourteen (14) calendar days after award of contract. Upload scoping report, post updates and summary reports, news releases, Federal Register notices, the ROD, and other relevant documents, other than the Draft and Final EIS links within one (1) calendar day of issuance. Upload the Draft and Final EIS links on the date the Notices of Availability (NOAs) are published. Upload the comment form on the date the NOA is issued for the Draft EIS.

#### Phase I – Task 8:  Create and Maintain the Administrative Record

The Contractor will create and maintain an administrative record for the EIS. The record will include all relevant Contractor and EIS-related agency records through the adoption of the ROD (approximately April 30, 2012). The process will be guided by “Guidance to Client Agencies on Compiling the Administrative Record” in the United States Attorneys’ Bulletin of February 2000. The administrative record will have search and retrieval capabilities as well as serve as an archive for paper and electronic documents. It will be designed to quickly prepare document packages for the Service, including documents requested under the Freedom of Information Act (FOIA). The administrative record will be updated on at least a biweekly basis, will be maintained throughout the EIS process, and will always be available for inspection by the Service.

Deliverable:   Paper and electronic versions of the administrative record.  Specific records upon request from the Service or in response to a FOIA request.

Due dates:  Final administrative record sixty (60) calendar days after completion of the Record of Decision; specific document requests within 3 working days.

Phase II

Phase II - Task 1:  Affected Environment

The Contractor will prepare a draft of the Affected Environment chapter of the EIS, addressing Service concerns and comments on the Specialists’ Reports.  Appendices supplementing the Affected Environment chapter will be developed and reviewed simultaneously. The COR will consolidate internal-review comments on the draft Affected Environment chapter and resolve any conflicts. The Contractor will incorporate the consolidated comments in the Internal Review Draft EIS.

Deliverable:  A draft annotated outline and at least one (1) version of the draft chapter for Service review prior to the Internal Review Draft EIS.

Due dates:  Draft Affected Environment chapter August 30, 2010

Phase II - Task 2:   Alternatives

As stated in the Act, the EIS shall contain an analysis of alternatives including the proposed land exchange and the potential construction and operation of a road between the communities of King Cove and Cold Bay, Alaska. .

Using all available information, the Contractor will propose a reasonable range of alternatives for the EIS (including those that will not be analyzed in detail).  The COR will coordinate cooperator review of the proposed range of alternatives and resolve any conflicts.  When the range of alternatives has been approved, the contractor will prepare a draft alternatives chapter. . The Contractor will incorporate the consolidated comments in the Internal Review Draft EIS.

Deliverables:  Draft range of alternatives.  Alternative Chapter for Service review prior to beginning drafting of the Environmental Consequences.

Due dates:  Alternative Chapter, June 30, 2010.

Phase II - Task 3: Environmental Consequences/Effect Analysis

The Contractor will prepare a draft of the Environmental Consequences chapter (Chapter IV), describing the adverse, beneficial, short-term, long-term, direct, indirect, and cumulative effects of the alternatives. The impact analysis will include descriptions of impact duration, intensity (or magnitude), and context (site-specific, local regional, or national effects). The analysis will include a discussion of the relationship between short-term uses of the environment and the maintenance and enhancement of long-term productivity, and any irreversible or irretrievable commitments of resources. In addition, the environmental consequences section will contain an in-depth analysis of the effects of climate change.  The draft will discuss the means of mitigating adverse environmental impacts (including all State and Federal permits that would be required if the action were implemented and any State/Federal regulations that would apply to a proposed action). Conclusions should be supported by analysis and the rationale clearly stated. The Contractor will develop Appendices supplementing Chapter IV simultaneously with the text.  The COR will consolidate internal-review comments on the draft Environmental Consequences chapter and resolve any conflicts. The Contractor will incorporate the consolidated comments in the Internal Review Draft EIS.

Deliverable:  A draft annotated outline and at least one (1) version of the Draft Environmental Consequences chapter for Service review prior to the Internal-review Draft EIS.

Due dates:  September 30, 2010

Phase II- Task 4:  Prepare and Distribute the Draft EIS

The Contractor will write and submit a complete Internal-Review Draft EIS (IDEIS) for Service review and comment (includes cooperators). The IDEIS will be due by December 30, 2010.  The Contractor will provide the COR with five (5) copies of the IDEIS on CD-ROM, five (5) paper copies and one (1) electronic version. The COR will consolidate internal-review comments on the Draft EIS and resolve any conflicts. The Contractor will incorporate necessary changes to the text and analysis and produce a paper and digital camera-ready draft document for Service approval to print. Upon approval by the COR, the Contractor will produce up to 2,000 CDs, distribute the CDs to the public, upload to the web, and provide the printer mailing lists and the appropriate digital files for printing. The product will conform to Service GIS standards. The Contractor will be responsible for all aspects of document publication and distribution, except printing and distributing paper copies. The Service will assume the costs of printing and distributing the document through a GPO print contract.

Deliverable: Internal-review Draft EIS; Draft EIS (digital files for printing paper copies, mailing labels, CDs for distribution to public); website upload

Due dates:  Internal-review Draft EIS due December 30, 2010

Subtask 1:  Essential Fish Habitat (EFH) Assessment

The Contractor will address impacts to EFH in the Draft EIS in a Section or Appendix clearly titled “Essential Fish Habitat”. As detailed in 50 CFR Section 600.920(e), the Section must identify affected EFH, assess impacts, and propose mitigation (if appropriate). The Assessment will be guided by the Regulations on Federal agency consultation in 50 CFR Section 600.905 Subpart K, and will be in accordance with the following:

- Contracted preparers will be qualified biologists with at least a Masters degree in biological sciences.

- The Contractor will collect available data, including interviewing knowledgeable individuals, to prepare the assessment.

- Contractor will draft consultation letters and draft the EFH Section or Appendix, but the Service will submit all official correspondence to NOAA Fisheries.

- The Contractor may talk directly with NOAA Fisheries. However, the Service COR will be apprised of pertinent issues and developments.

- The Contractor shall draft a response to the EFH Conservation Recommendations of NOAA Fisheries. Upon approval by the Service, this response will be incorporated in the Final EIS.

Deliverable:  Draft EFH Assessment (included as part of Draft EIS); Final EHF Assessment (included in Final EIS)

Due Dates:  Draft EFH Assessment due December 30, 2010.

Subtask 2:  Conduct ANILCA 810 Analysis

The Contractor shall conduct an ANILCA 810 analysis in the Draft EIS in a Section or Appendix clearly titled “ANILCA 810 Analysis”.  As detailed in ANILCA 810 (Appendix A), the Contractor must analyze all effects of the project on subsistence use.  The Contractor needs to adhere to Service guidelines when preparing the ANILCA 810 analysis.

Deliverable:  Draft ANILCA 810 analysis (included as part of Draft EIS); Final ANILCA 810 analysis (included in Final EIS)

Due Dates:  Draft ANILCA 810 analysis due December 30, 2010

Phase III

Phase III- Task 1:  Revise DEIS/Solicit Comments: Draft EIS/ANILCA 810

The Contractor shall address all internal review comments and edits and prepare the DEIS for publication. The Contractor will solicit public comments by drafting a news release (to be approved by the Service), producing an update summarizing alternatives and providing information on commenting on the Draft EIS, uploading a Comment Form on the EIS website, and by organizing and facilitating public meetings (including ANILCA 810 hearings, if required) for soliciting review comments. The Contractor will develop a PowerPoint presentation (to deliver at public meetings) summarizing the environmental consequences for each alternative. Regarding meetings/hearings, the Contractor will:

- Prepare and publish meeting announcements; prepare radio (PSA) and newspaper announcements; send flyers (meeting announcements) to villages for posting in public areas.

- Prepare handout material (i.e. sign-in sheets, maps, posters, project summary, updates) and a PowerPoint presentation for the public meetings

- Facilitate public meetings/hearings during the comment period. Meetings/hearings will occur in the same communities as scoping meetings.

- Transcribe the oral comments of each public meeting.

- Match the sign-in sheets at each public meeting to the master mailing list and update the mailing list.

- Provide an electronic comment form on the website to obtain comment on the Draft EIS.

Deliverable:  Revise DEIS by addressing internal comments.  Prepare advertisements; flyers; PSAs; update; meeting materials; PowerPoint presentation; facilitated public meetings; transcription of meetings/hearings testimony; comment form on website.

Due Dates:  	Draft EIS, publication ready:  March 31, 2011

Advertisements; flyers; PSAs; update; meeting materials; PowerPoint presentation; comment form on website; due to the Service at least 10 days prior to the first scheduled public meeting (April 2011 – June 2011).

Facilitating public meetings; and transcription of meetings/hearings testimony; due on scheduled dates for public meetings, with meetings being scheduled no earlier than 10 days after the date of the Federal Register NOA (April 2011 – June 2011).

Phase III- Task 2:   Comment Analysis Database

The Contractor will develop a database system to manage the analysis of and response to comments on the Draft EIS. There is the potential for thousands (perhaps tens of thousands) of comments, including many form letters as well as unique comments. The database will record all comments, identify unique comments, record responses to the comments (entered by appropriate Contractor employee or by Service staff if response is policy-related), and identify proposed changes in EIS text, tables, or figures to address specific comments. The contractor will provide the COR with a compiled list of public comments organized by issue and impact topic. At the direction of the COR, the Contractor will provide copies of all comment letters, forms, transcripts of meetings, etc. to the Service and cooperating agencies. The Service will respond to requests from other entities.

Deliverable:  Database of parsed comments; compiled list of public comments organized by issue and impact topic; paper and/or CD-ROM copies of all comments letters, forms, transcripts of meetings, etc.; database of responses and changes to be made for the Final EIS.

Due Dates:  September 30, 2011

Phase IV

Phase IV - Task 1:  Prepare and Distribute the Final EIS

The Contractor will review all comments and identify comments requiring response, recommend how the EIS will be revised to address comments, and draft responses to be included in the Internal-review Final EIS. The Service will prepare responses to policy-related comments. The Contractor will prepare the Internal-review Final EIS. The Contractor will provide the COR with five (5) copies on CD-ROM and five (5) paper copies. The COR will consolidate internal review comments and resolve any conflicts. The Contractor will make necessary changes to the text and analysis and produce a digital camera-ready draft in pdf. and Word document for Service approval. Upon approval by the COR, the Contractor will produce up to 2,000 CDs, distribute the CDs to the public, upload to the web, and provide the printer with mailing labels and the appropriate digital files for printing. The Contractor will be responsible for all aspects of document publication and distribution, except printing and distributing paper copies. The Service will assume the costs of printing and distributing the document through a GPO print contract.

Deliverable:  Internal-review Final EIS; Final EIS (mailing labels and digital files for production of paper copy; CDs for distribution to public); website upload

Due dates:  Preliminary Final EIS March 30, 2012; Final EIS April 30, 2012

Phase IV - Task 2:  Print and Distribute the Record of Decision (ROD)

The Service will draft the Record of Decision, addressing any public comments received during the 30 day 'no action' period after releasing the Final EIS. The Contractor will produce and distribute up to 2,000 CDs of the ROD, upload to the web, and print and distribute up to 1,000 paper copies.  The Contractor is responsible for all aspects of document publication and distribution.

VI. Deliverables

If not otherwise stated in the task order, the following requirements generally apply to all deliverables submitted:

All deliverables must be sent to COR Stephanie Brady by express U.S. mail or Peninsula Air small package express service.  Deliverables will be addressed to -

Stephanie Brady

US Fish and Wildlife Service

PO Box 277

King Salmon, Alaska  99613

Phone: (907) 246-1203;

Stephanie_Brady@fws.gov

The Contractor is responsible for submitting deliverables on time. Section V includes a tentative schedule, however the Service and the Contractor will agree to the final project schedule for deliverables in the Final Work Plan. It is not acceptable if a product is submitted to meet a time frame, but does not meet Service requirements detailed in the Statement of Work. The Service encourages the Contractor to work closely with Service specialists to avoid major revisions of initial submissions. The Service expects that most documents will be revised satisfactorily after only one review.

All submitted deliverables must:

- meet Service requirements (quality standards), as required by laws, regulations, and guidance; and

- be approved by the Service’s COR before being considered satisfactory.

General submission guidelines:

1.	Software:  Electronic word processing documents will be in Microsoft Word. The GIS software will be ESRI ArcGIS and ArcIMS (Version 9). The final environmental documents may be in Adobe InDesign or similar desktop publishing software.

2.   Media:  Deliverables will be paper copies, and/or electronic copies (including CDs), as specified. Electronic files or CDs will be provided for all documents requiring internal Service review. If copy media is unspecified, the Service will have the option to request either paper copies or electronic files. Many transmittals will be sent electronically.

3.	Drafts:  The Contractor will provide the Service with the requested number of paper copies for each submission of draft documents (e.g., the preliminary draft and preliminary final EIS, etc.), and electronic files via electronic transmission or CD-ROM.

4.	Printing:  All printed documents will conform to Service publication standards as identified by the COR. The Contractor will be responsible for printing and distributing all documents, except the Draft EIS and Final EIS.

5.	Miscellaneous Public Involvement Deliverables:  The Contractor will plan and facilitate public meetings, secure meeting rooms, prepare updates, news releases, mailings, newspaper advertisements, radio announcements, Federal Register notices, brochures/booklets/pamphlets and PowerPoint presentations. Certain products must be website compatible.

6.	Executive Summary: The Scoping Report, Specialist Reports, Draft EIS, Final EIS, and other major documents associated with this plan will include a concise executive summary that summarizes the purpose of the document and all major points (see NEPA regulations).

7.	GIS:

- The Contractor will provide the Service with electronic copies of all geospatial deliverables. The Service GIS system operates on Windows NT and Windows XP using ArcGIS (v. 9.x) software. All geospatial deliverables will comply with applicable Service and Federal geographic information standards, particularly those determined by the Federal Geographic Data Committee (FDGC) as supporting the National Spatial Data Infrastructure (NSDI). The Contractor will provide complete geospatial data (spatial component, attribute information, and metadata) in the ArcGIS file geodatabase format.

- At the COR’s request, the Contractor will provide datasets and mxd’s for individual data layers developed throughout the EIS process. These data will be included on the project website and/or be provided on CD-ROM, at the discretion of the COR.

- The Contractor will not use proprietary software or extensions that may hinder sharing map documents with the government or other contractors.

- Contractor will have a single point of contact for GIS data exchange between the Service and the Contractor.

- All final GIS data will be in the Alaska Albers Equal Area Conic projection (Horizontal Datum:  NAD83, Central Meridian:  154).  Acquiring new data will require COR approval. New data will be converted to Service data standards, whenever feasible.

VII. 	Invoicing

Invoices shall be submitted monthly to the COR.  The COR will forward to the CO for approval and payment.

VIII.	Contracting Officer's Representative (COR) and Project Inspector (PI)

COR

Stephanie Brady

US Fish and Wildlife Service

PO Box 277

King Salmon, Alaska  99613

Phone: (907) 246-1203;

Stephanie_Brady@fws.gov

PIs

Mike Boylan

Fish and Wildlife Service

Refuge Supervisor, North

1011 E. Tudor Road

Anchorage, Alaska  99503

Phone: (907) 786-3355

Mike_boylan@fws.gov

Helen Clough

Fish and Wildlife Service

Division Chief, Conservation Planning and Policy

1011 E. Tudor Road

Anchorage, Alaska  99503

Helen_clough@fws.gov

Appendix A

| Category | Title |
| --- | --- |
| Proposed Land Exchange |  |
|  | Omnibus Public Land Management Act of 2009 (H.R. 146, Subtitle E) http://frwebgate.access.gpo.gov/cgi-bin/getdoc.cgi?dbname=111_cong_bills&docid=f:h146enr.txt.pdf |
| CEQ Guidance |  |
|  | 40 CFR 1500-1508 |
|  | Forty Most Asked Questions |
|  | Transboundary Impacts |
|  | Environmental Justice |
|  | Considering Cumulative Effects |
|  | Executive Orders |
|  | Plain Language Tools |
|  | Considering Cumulative Effects in EPA Review |
|  | Environmental Justice Final Guidance |
|  | Air Pollution Emission Factors AP-42 Volume 1, Fifth Edition |
|  | EPA EIS Rating Criteria |
|  | How to File an EIS |
| Essential Fish Habitat Guidance |  |
|  | Essential Fish Habitat Consultation Guidance |
|  | Preparing Essential Fish Habitat Assessments: A Guide for Federal Action Agencies |

| Service Manual and Handbook Guidance |  |
| --- | --- |
| Manual Guidance |  |
| Service Manual 602 FW 1 | Refuge Planning |
| Service Manual 603 FW 2 | Refuge Compatibility |
| Service Manual 340 FW 3 | Rights-of-way and Road Closings |
| Service Manual 550 FW 1-3 | NEPA |
| Service Manual 601 FW 3 | Biological Integrity, Diversity, And Environmental Health |
| Service Manual 613 FW 2 | Wetlands Protection |
| Service Manual 660 FW 1 | Wetlands Policy and Action Plan |
| Service Manual 614 FW 4 | Cultural Resources – Planning, Protection, and Management |
| Service Manual 602 FW 3 | Refuge Comprehensive Conservation Planning Process |
| Service Manual 716 FW1-4 | Inter-jurisdictional Fisheries (Not on Web) |
| Service Manual 720 FW1 | Migratory Birds – Policies and Responsibilities of the Migratory Bird Management Program |
| Service Manual 721 FW2 | North American Waterfowl Management Plan |
| Service Manual 730-739 FW | Endangered Species (not on Web) |
| Service Manual 601 FW 1 | National Wildlife Refuge System – NWRS Mission, Goals and Purposes (not on web) |
| Service Manual 611 FW3 | Special Areas Management - Wild and Scenic Rivers (not on Web) |
| Service Manual 613 FW 2 | Wetlands Protection |
| Service Manual 121 FW 1-12 | Printing and Publishing (Draft; not on Web) |
| Handbook Guidance |  |
|  | Graphic Standards (not on Web) |
|  | Endangered Species Section 7 Consultation |
|  | Federal/State Environmental Compliance |
|  | Service NEPA Reference |
|  | Correspondence |
| Service Policy |  |
|  | Biological diversity, Integrity and Environmental Health of the NWRS |
|  | Compatibility |
|  | NWRS Mission and Goals and Refuge Purposes (Draft) |
|  | Wilderness Stewardship (Draft) |

| Statutes |  |  |
| --- | --- | --- |
|  | Alaska Native Claims Settlement Act (ANCSA), as amended, 43 U.S.C. 1601 et seq. |  |
|  | Alaska National Interest Lands Conservation Act, as amended, 16 U.S.C. and 43 U.S.C. Alaska National Interest Lands Conservation Act, as amended, 810 analysis for effects on subsistence uses |  |
|  | National Wildlife Refuge System Improvement Act of 1997, 16 U.S.C. 668dd |  |
|  | Federal Land Policy and Management Act of 1976 (FLPMA), as amended, 43 U.S.C. 1701 et seq., |  |
|  | National Environmental Policy Act of 1969 (NEPA), as amended, 42 U.S.C. 4321 et seq |  |
|  | Clean Air Act of 1990, as amended, 42 U.S.C. 7418 et seq. |  |
|  | Clean Water Act of 1987, as amended, 33 U.S.C. 1251 et seq. |  |
|  | Federal Water Pollution Control Act, as amended, 33 U.S.C. 1323 et seq. |  |
|  | Safe Drinking Water Act, as amended, 42 U.S.C. 201 et seq. |  |
|  | Endangered Species Act (ESA) of 1973, as amended, 16 U.S.C. 1531 et seq. |  |
|  | Wilderness Act, as amended, 16 U.S.C. 1131 et seq. |  |
|  | Antiquities Act of 1906, as amended, 16 U.S.C. 431-433. |  |
|  | National Historic Preservation Act (NHPA), as amended, 16 U.S.C. 470 et seq. |  |
|  | American Indian Religious Freedom Act of 1978, as amended, 42 U.S.C. 1996 et seq. |  |
|  | Recreation and Public Purposes Act of 1926, as amended, 43 U.S.C. 869 et seq. |  |
|  | Archaeological Resources Protection Act of 1970, as amended, 42 U.S.C 1996 et seq. |  |
|  | Migratory Bird Conservation Act of 1979, as amended, 16 U.S.C. 715 et seq. |  |
|  | Native American Graves Protection and Repatriation Act of 1990, as amended, 25 U.S.C. 3001 et seq. |  |
| Executive and Secretarial Orders |  |  |
|  | Executive Orders 11644 and 11989 (Off-Road Vehicles) |  |
|  | Executive Order 12898 (Federal Actions to Address Environmental Justice in Minority Populations and Low Income Populations |  |
|  | Executive Order 13007 (Indian Sacred Sites) |  |
|  | Executive Order 13112 (Invasive Species) |  |
|  | Executive Order 13175 (Consultation and Coordination with Indian Tribal Governments) |  |
|  | Executive Order 11988 (Floodplain Management) |  |
|  | Executive Order 11990 (Protection of Wetlands) |  |
|  | Executive Order 13186 (Migratory Birds) |  |
|  | Executive Order 13045 (Protection of Children from Environmental Health Risks and Safety Risks |  |
|  | Executive Order 12144 (Environmental Effects Abroad of Major Federal Actions) |  |
|  | Secretarial Order 3175 (incorporated into the Departmental Manual at 512 DM 2) |  |
|  | Secretarial Order 3206 (American Indian Tribal Rights, Federal-Tribal Trust Responsibilities, and the Endangered Species Act) |  |
| Miscellaneous |  |  |
|  | Plain Language |  |

APPENDIX B: PRELIMINARY ENVIRONMENTAL IMPACT STATEMENT OUTLINE

SUMMARY

TABLE OF CONTENTS

PURPOSE AND NEED

Project Background and Scope

Purpose

Need

Decisions that must be made

Significant Issues and Objectives

Impact Topics Selected for Detailed Analysis

[Potential resource impact topics include wilderness values, T&E species, fish and wildlife, water quality and quantity, hydrologic processes, air quality, greenhouse gas emissions, soils and geology, socio-economics, subsistence, cultural resources. Potential cultural resource impact topics include historic, archeological, and ethnographic resources]

Issues Dismissed from Detailed Analysis

PROPOSAL AND ALTERNATIVES

No Action

Alternatives Considered but Dismissed

Alternative A (Proposed Action)

Selection of the Preferred Alternative (If appropriate)

Environmentally Preferred Alternative

Impact Comparison Matrix

Other Summaries [Alternative Features, How Each Alternative Meets Requirements of §101 and 102(1) of NEPA]

(Appropriate measures should be built into each action alternative)

# AFFECTED ENVIRONMENT

Wilderness Resources

Fish (including EFH)

T&E species

Wildlife

Flora

Wetlands

Hydrologic Processes

Water Resources

Air Quality, including greenhouse gas emissions

Archeological/Cultural Resources

Social Factors (subsistence, way of life, population dynamics,)

Economic Factors

Refuge Integrity

Other topics as needed

# ENVIRONMENTAL CONSEQUENCES

Impact Analysis Methods

Effects of Alternative A (Proposed Action)

Impact Analysis

Impairment Analysis

Cumulative Effects

Conclusion

All Other Impact Topics

etc.

Sustainability and Long-Term Management

Relationship between local short-term uses of the environment and the maintenance and enhancement of long-term productivity

Any Irreversible/Irretrievable Commitments of Resources that would be involved if the alternative were implemented

Any adverse impacts that could not be avoided if the action were implemented

Effects of Alternative B (No Action Alternative)

etc.

Effects of Alternative C

etc,

CONSULTATION AND COORDINATION

History of Public Involvement

List of Preparers

List of Recipients

# REFERENCES

Bibliography

Glossary

Index

Appendixes