## General
Pre-NOI |  |  |  |  | NOI |  | DEIS | [9 empty] | FEIS | [6 empty] | ROD | All Authorizations Issued
NEPA Planning Document | Complete Application Received | Initial Action Notice - Review Team Review | NOI - Review Team Review | OES/PPM Review | NOI Publication | NOI and Scoping Public Comment Period | DEIS Development Oral Breifing | DEIS Development Review Team Review | Address DOI Comments/Concerns | Write DEIS | Internal FWS Review | DEIS and NOA Clearance Review Team Review | Address DOI Comments/Concerns | OES/PPM Review / EPA Coordination | DEIS and NOA Publication | DEIS Public Comment Period | Write FEIS | FEIS and NOA Clearance Review Team Review | Address DOI Comments/Concerns | OES/PPM Review | FEIS Published | FEIS Final Review Period | Review Team Review | Final ROD Published
TBD | - | 2 Days | 3 Days | TBD | - | 30 Days | - | 5 Days | TBD | TBD | TBD | 10 Days | TBD | TBD | - | 45 Days | TBD | 5 Days | TBD | TBD | - | 30 Days | 3 Days | - | -
[15 empty] | 90 Day | [6 empty] | 31 Days or More
1 Year