## budget detail entire project
MOUSE ERADICATION BUDGET: Farallon IslandS Seabird Habitat Restoration Project
Projected Budget
May 30, 2006 vs. June 29, 2010 estimated costs
|  | Year 1 |  |  |  | Year 2 |  | Year 3 |  | Year 4 |  | Year 5 |  | Total
|  | Environmental Compliance |  |  |  | R&M |  | Implementation |  | Post Eradication Monitoring
|  | 2006 | 2007-2009 | 2010 | 2007-10 | 2006 | 2010 | 2006 | 2010 | 2006 | 2010 | 2006 | 2010 | 2006 | 2007-09 | 2010 | 2007-10
Island Conservation (Eradication Experts)
Salaries & Benefits
| Project Leader/Eradication Expert | 48325 | 20040.6321 | 11901.0502 | 31941.6822 | 17788.5 | 15990.386 | 46807.875 | 75342.555 | 30150 | 41087.6759 | 19500 | 20684.0523 | 162571.375 | 20040.6321 | 165005.7195 | 185046.3515
| IC Executive Director | 3750 | 5917.7837 | 942.5928 | 6860.3765 | 0 | 1963.8752 | 0 | 11027.6794 | 0 | 3065.3425 | 0 | 1771.5179 | 3750 | 5917.7837 | 18771.0078 | 24688.7915
| US Director | 4025 | 4415.2967 | 8584.5603 | 12999.857 | 0 | 2547.2045 | 0 | 24132 | 0 | 6637.2894 | 0 | 971.5608 | 4025 | 4415.2967 | 42872.6151 | 47287.9117
| Project Support Coordinator | 20125 | 1409.0638 | 0 | 1409.0638 | 6500 | 12024.7703 | 12500 | 39945 | 3500 | 16442.7852 | 0 | 8158.5948 | 42625 | 1409.0638 | 76571.1503 | 77980.2141
| IT Manager | 5750 |  | 2008.1798 | 2008.1798 | 0 | 855.5496 | 7500 | 11472.2282 | 0 | 0 | 0 | 0 | 13250 | 0 | 14335.9576 | 14335.9576
| Science Writer | 4945 | 59786.3548 | 8782.6572 | 68569.0119 | 0 | 580.2591 | 0 | 6966 | 0 | 4186 | 0 | 2093 | 4945 | 59786.3548 | 22607.9163 | 82394.2711
| IC Field Biologists | 0 |  | 0 | 0 | 26314.875 | 8137.9552 | 25000 | 10212.8904 | 4500 | 5036.4709 | 8475 | 5053.9226 | 64289.875 | 0 | 28441.2391 | 28441.2391
Subtotal |  | 86920 | 91569.131 | 32219.0402 | 123788.1712 | 50603.375 | 42100 | 91807.875 | 179098.353 | 38150 | 76455.5639 | 27975 | 38732.6485 | 295456.25 | 91569.131 | 368605.6056 | 460174.7366
Equipment
| Traps | 0 |  |  | 0 | 2500 | 3300 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 3300 | 3300
Subtotal |  | 0 | 0 | 0 | 0 | 2500 | 3300 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 3300 | 3300
Travel/Transport
| Boat transport | 1600 |  |  | 0 | 10000 | 0 | 20000 | 15000 | 7500 | 5000 | 7500 | 5000 | 46600 | 0 | 25000 | 25000
| Helicopter Support | 0 |  | 0 | 0 | 3500 | 0 | 35000 | 35172 | 3500 | 0 | 3500 | 0 | 45500 | 0 | 35172 | 35172
| Eradication expert pilot | 0 |  | 0 | 0 | 0 | 0 | 0 | 5800 | 0 | 0 | 0 | 0 | 0 | 0 | 5800 | 5800
| Emergency evacuation insurance | 0 |  | 0 | 0 | 0 | 325 | 0 | 1433 | 0 | 404 | 0 | 232 | 0 | 0 | 2394 | 2394
| Travel of Technical Experts | 0 | 6900.31 | 5226 | 12126.31 | 0 | 6972 | 0 | 19017 | 0 | 5823 | 0 | 3125 | 0 | 6900.31 | 40163 | 47063.31
| Housing of Technical Experts | 2200 | 2063.6839 | 1620 | 3683.6839 | 9450 | 4379 | 4500 | 9239 | 2500 | 2993 | 1500 | 2228 | 20150 | 2063.6839 | 20459 | 22522.6839
| Rental vehicle | 0 |  | 0 | 0 | 0 | 1920 | 0 | 720 | 0 | 300 | 0 | 300 | 0 | 0 | 3240 | 3240
| Field per diem | 0 | 2410.7307 | 1031 | 3441.7307 | 4500 | 4230 | 4500 | 6469 | 1350 | 2721 | 1350 | 2298 | 11700 | 2410.7307 | 16749 | 19159.7307
Subtotal |  | 3800 | 11374.7245 | 7877 | 19251.7245 | 27450 | 17826 | 64000 | 92850 | 14850 | 17241 | 13850 | 13183 | 123950 | 11374.7245 | 148977 | 160351.7245
Materials and Supplies
| Radio Collars (House Mice) | 0 |  | 0 | 0 | 4500 | 3000 | 4500 | 5000 | 0 | 0 | 0 | 0 | 9000 | 0 | 8000 | 8000
| Research Supplies: Helicopter PPE (Nomax clothing, gloves, helmets, eye protection) | 0 |  | 0 | 0 | 9500 | 1124 | 7500 | 5200 | 1000 | 4042 | 1000 | 3038 | 19000 | 0 | 13404 | 13404
| Bait stations | 0 |  | 0 | 0 | 0 | 0 | 0 | 3151 | 0 | 0 | 0 | 0 | 0 | 0 | 3151 | 3151
| Bait and supplies | 0 | 6396.5625 | 0 | 6396.5625 | 2400 | 2025 | 18000 | 19000 | 0 | 0 | 0 | 0 | 20400 | 6396.5625 | 21025 | 27421.5625
| Bait shipping & helicopter bucket transport | 0 |  | 0 | 0 | 0 | 855 | 0 | 5243 |  |  |  |  | 0 | 0 | 6098 | 6098
Subtotal |  | 0 | 6396.5625 | 0 | 6396.5625 | 16400 | 7004 | 30000 | 37594 | 1000 | 4042 | 1000 | 3038 | 48400 | 6396.5625 | 51678 | 58074.5625
Stakeholder Coordination and Public Outreach
| Videography | 0 |  | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0
| Outreach Materials and Coordination | 4400 |  | 4463 | 4463 | 12500 | 0 | 7500 | 2500 | 2500 | 1500 | 2500 | 2500 | 29400 | 0 | 10963 | 10963
Subtotal |  | 4400 | 0 | 4463 | 4463 | 12500 | 0 | 27500 | 2500 | 2500 | 1500 | 2500 | 2500 | 49400 | 0 | 10963 | 10963
Grants to Others
| Toxicological Analysis | 0 |  | 0 | 0 | 0 | 0 | 21000 | 20000 | 0 | 5000 | 0 | 0 | 21000 | 0 | 25000 | 25000
| Non-Target Bird Mitigation/Risk Analysis | 0 |  | 0 | 0 |  | 15425 | 24156 | 25000 | 0 | 0 | 0 | 0 | 24156 | 0 | 40425 | 40425
| Introduction Prevention Plan | 0 |  | 0 | 0 | 12000 | 0 | 10000 | 0 | 10000 | 0 | 0 | 0 | 32000 | 0 | 0 | 0
Subtotal |  | 0 |  | 0 | 0 | 12000 | 15425 | 55156 | 45000 | 10000 | 5000 | 0 | 0 | 77156 | 0 | 65425 | 65425
Project Expenses
| Professional services | 0 | 49427.4492 | 1883 | 51310.4492 | 0 | 3745 | 0 | 18385 | 0 | 5181 | 0 | 2983 | 0 | 49427.4492 | 32177 | 81604.4492
| Occupany expense | 0 | 3078.3848 | 1002 | 4080.3848 | 0 | 2220 | 0 | 10788 | 0 | 2760 | 0 | 1614 | 0 | 3078.3848 | 18384 | 21462.3848
| Project services | 0 | 2093.418 | 315 | 2408.418 | 0 | 767 | 0 | 3301 | 0 | 998 | 0 | 575 | 0 | 2093.418 | 5956 | 8049.418
Subtotal |  | 0 | 54599.2519 | 3200 | 57799.2519 | 0 | 6732 | 0 | 32474 | 0 | 8939 | 0 | 5172 | 0 | 54599.2519 | 56517 | 111116.2519
Island Conservation Subtotal |  | 95120 | 163939.67 | 47759.0402 | 211698.7102 | 121453.375 | 92387 | 268463.875 | 389516.353 | 66500 | 113177.5639 | 45325 | 62625.6485 | 596862.25 | 163939.67 | 705465.6056 | 869405.2756
Island Conservation Overhead (2006: 30%; 2010: 15.7% of Sub-Total) |  | 28536 | 23650.29 | 7530.1679 | 31180.4579 | 36436.0125 | 14566.6583 | 80539.1625 | 61415.0434 | 19950 | 17844.7065 | 13597.5 | 9874.186 | 179058.675 | 23650.29 | 111230.762 | 134881.052
Island Conservation Contract Total |  | 123656 | 187589.96 | 55289.2081 | 242879.1681 | 157889.3875 | 106953.6583 | 349003.0375 | 450931.3963 | 86450 | 131022.2704 | 58922.5 | 72499.8345 | 775920.925 | 187589.96 | 816696.3676 | 1004286.3276
PRBO Contract (Island Biology Specialists) |  | 8000 |  |  |  | 10500 | 12500 | 12500 | 12500 | 8000 | 8000 | 0 | 0 | 39000 | 0 | 33000 | 33000
Contracts (Pass-through) Total |  | 131656 | 187589.96 | 55289.2081 | 242879.1681 | 168389.3875 | 119453.6583 | 361503.0375 | 463431.3963 | 94450 | 139022.2704 | 58922.5 | 72499.8345 | 814920.925 | 187589.96 | 849696.3676 | 1037286.3276
U.S. Fish and Wildlife Service (FWS)
FWS Operating Costs
| FWS Project Manager | 38400 | 0 | 0 | 0 | 49125 | 38945 | 49125 | 39763.2534 | 34500 | 20300 | 20000 | 20300 | 191150 | 0 | 119308.2534 | 119308.2534
| FWS Admin Support | 0 | 0 | 0 | 0 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 2000 | 2000 | 17000 | 0 | 17000 | 17000
| Outboard Gas/Oil/Maintenance/Other | 0 | 0 | 0 | 0 | 3000 | 3000 | 2500 | 2500 | 500 | 500 | 500 | 500 | 6500 | 0 | 6500 | 6500
| Final EA Printing | 0 | 0 | 1500 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 1500
| Introduction Prevention Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 5000 | 0 | 0 | 0 | 0 | 10000 | 10000
FWS Subtotal (Direct Costs) |  | 38400 | 0 | 1500 | 1500 | 57125 | 46945 | 56625 | 52263.2534 | 40000 | 30800 | 22500 | 22800 | 214650 | 0 | 154308.2534 | 154308.2534
FWS Indirect Cost Recovery
FWS Direct Cost Recovery (29.5%) |  | NA | NA | 442.5 | 442.5 | 16851.875 | 13848.775 | 16704.375 | 15417.6598 | 11800 | 9086 | 6637.5 | 6726 | 51993.75 | 0 | 45520.9348 | 45520.9348
FWS Pass Through Recovery (6%) |  | NA | NA | 3317.3525 | 3317.3525 | 10103.3633 | 7167.2195 | 21690.1823 | 27805.8838 | 5667 | 8341.3362 | 3535.35 | 4349.9901 | 40995.8955 | 0 | 50981.7821 | 50981.7821
FWS Total |  | 38400 |  | 5259.8525 | 38400 | 84080.2382 | 67960.9945 | 95019.5572 | 95486.7969 | 57467 | 48227.3362 | 32672.85 | 33875.9901 | 307639.6455 | 0 | 250810.9702 | 250810.9702
NOAA Intertidal Fish Surveys & Report |  | 0 | 0 | 0 | 0 | 0 | 7500 | 0 | 7500 | 15000 | 0 | 0 | 0 | 15000 | 0 | 15000 | 15000
PROJECT TOTAL |  | 170056 | 187589.96 | 60549.0606 | 281279.1681 | 252469.6258 | 194914.6528 | 456522.5947 | 566418.1933 | 166917 | 187249.6066 | 91595.35 | 106375.8246 | 1137560.5705 | 187589.96 | 1115507.3378 | 1303097.2978
Request to Luckenbach
IC Estimated 2010 Project Total Year 1-5 |  | 1004286.3276 |  | 2006 reflects original budget.
| minus NFWF funding | -149500 |  | 2007-2009 reflects actual spent in that period.
| minus IC contribution | -75000 |  | 2010 reflects revised estimate of funds needed for the entire project.
IC Current Ask From Luckenbach |  | 779786.3276 |  | 2007-10 reflects revised estimated total cost of project.
PRBO |  | 33000
FWS |  | 250810.9702
GFNMS |  | 15000
TOTAL Request |  | 1078597.2978
Allocated Total budget |  | 992313
Difference |  | 86284.2978
15% contingency |  | 148846.95
IC: Original Ask from Luckenbach |  | 654820
IC: Budget shortfall |  | 124966.3276
IC: 15% contingency |  | 155153
Note on L32: StaceyBuckelew: 1,250 snap traps wax supplies detection supplies replacement bait stations
Note on N32: StaceyBuckelew: detection supplies replacement snap traps replacement wax supplies replacement bait stations

## budget detail 2010
|  | Environmental Compliance | R&M | Total
Island Conservation (Eradication Experts)
Salaries & Benefits
| Project Leader/Eradication Expert | 11901.0502 | 15990.386 | 27891.4362
| IC Executive Director | 942.5928 | 1963.8752 | 2906.468
| US Director | 8584.5603 | 2547.2045 | 11131.7649
| Project Support Coordinator | 0 | 12024.7703 | 12024.7703
| IT Manager | 2008.1798 | 855.5496 | 2863.7294
| Science Writer | 8782.6572 | 580.2591 | 9362.9163
| IC Field Biologists | 0 | 8137.9552 | 8137.9552
Subtotal |  | 32219.0402 | 42100 | 74319.0402
Equipment
| Traps |  | 3300 | 3300
Subtotal |  | 0 | 3300 | 3300
Travel/Transport
| Boat transport | 0 | 0 | 0
| Helicopter Support | 0 | 0 | 0
| Eradication expert pilot | 0 | 0 | 0
| Emergency evacuation insurance | 0 | 325 | 325
| Travel of Technical Experts | 5226 | 6972 | 12198
| Housing of Technical Experts | 1620 | 4379 | 5999
| Rental vehicle | 0 | 1920 | 1920
| Field per diem | 1031 | 4230 | 5261
Subtotal |  | 7877 | 17826 | 25703
Materials and Supplies
| Radio Collars (House Mice) | 0 | 3000 | 3000
| Research Supplies: Helicopter PPE (Nomax clothing, gloves, helmets, eye protection) | 0 | 1124 | 1124
| Bait stations | 0 | 0 | 0
| Bait and supplies | 0 | 2025 | 2025
| Bait shipping & helicopter bucket transport | 0 | 855 | 855
Subtotal |  | 0 | 7004 | 7004
Stakeholder Coordination and Public Outreach
| Outreach Materials and Coordination | 4463 | 0 | 4463
Subtotal |  | 4463 | 0 | 4463
Grants to Others
| Toxicological Analysis | 0 | 0 | 0
| Non-Target Bird Mitigation/Risk Analysis | 0 | 15425 | 15425
| Introduction Prevention Plan | 0 | 0 | 0
Subtotal |  | 0 | 15425 | 15425
Project Expenses
| Professional services | 1883 | 3745 | 5628
| Occupany expense | 1002 | 2220 | 3222
| Project services | 315 | 767 | 1082
Subtotal |  | 3200 | 6732 | 9932
Island Conservation Subtotal |  | 47759.0402 | 92387 | 140146.0402
Island Conservation Overhead (2006: 30%; 2010: 15.7% of Sub-Total) |  | 7530.1679 | 14566.6583 | 22096.8262
Island Conservation Contract Total |  | 55289.2081 | 106953.6583 | 162242.8664
PRBO Contract (Island Biology Specialists) |  | 0 | 12500 | 12500
Contracts (Pass-through) Total |  | 55289.2081 | 119453.6583 | 174742.8664
U.S. Fish and Wildlife Service (FWS)
FWS Operating Costs
| FWS Project Manager | 0 | 38945 | 38945
| FWS Admin Support | 0 | 5000 | 5000
| Outboard Gas/Oil/Maintenance/Other | 0 | 3000 | 3000
| Final EA Printing | 1500 | 0 | 1500
| Introduction Prevention Plan | 0 | 0 | 0
FWS Subtotal (Direct Costs) |  | 1500 | 46945 | 48445
FWS Indirect Cost Recovery
FWS Direct Cost Recovery (29.5%) |  | 442.5 | 13848.775 | 14291.275
FWS Pass Through Recovery (6%) |  | 3317.3525 | 7167.2195 | 10484.572
FWS Total |  |  | 67960.9945 | 73220.847
NOAA Intertidal Fish Surveys & Report |  | 0 | 7500 | 7500
PROJECT TOTAL |  | 55289.2081 | 194914.6528 | 255463.7134