SCOPE OF WORK/BUDGET

BETWEEN

UNITED STATES DEPARTMENT OF INTERIOR

FISH AND WILDLIFE SERVICE

at

FARALLON NATIONAL WILDLIFE REFUGE

and

UNITED STATES DEPARTMENT OF AGRICULTURE

ANIMAL AND PLANT HEALTH INSPECTION SERVICE

NATIONAL WILDLIFE RESEARCH CENTER

4/1/2016 – 11/15/2016

PROJECT TITLE:  A preliminary assessment of the potential hazards of the anticoagulants diphacinone and brodificoum to arboreal salamanders

OBJECTIVE

The objective of this project is to determine if exposure to the anticoagulants diphacinone and brodifacoum is lethal to Farallon arboreal salamanders (Aneides lugubris farallonensis).   This information will be used in analyses of potential impacts to arboreal salamanders in the Environmental Impact Statement (EIS) for the South Farallon Islands House Mouse Eradication Project.

SCOPE OF WORK

Invasive rodents cause much damage to island ecosystems and anticoagulant rodenticides are an essential tool for the eradication of invasive rodents on islands.  The anticoagulants brodificoum and diphacinone have been proposed as alternatives in a draft EIS by the U.S. Fish and Wildlife Service (USFWS) to eradicate invasive house mice from the Farallon National Wildlife Refuge.  However, anticoagulant rodenticides may pose hazards to non-target animals.  This can occur through the direct consumption of the rodenticide material or from indirect exposure in which case the non –target animal consumes prey (rodents or insects) or scavenges on dead rodents that have previously consumed the anticoagulant bait.

For this study, the U.S. Department of Agriculture (USDA) will use live-captured or purchased salamanders to do a preliminary assessment of the potential hazards of the anticoagulants brodificoum and diphacinone to those animals.  Three routes of exposure will be examined: 1) allowing salamanders to feed on crushed anticoagulant pellets (direct internal exposure), 2) allow the salamanders to consume insects that have fed upon anticoagulant pellets (indirect internal exposure), and 3) spraying salamanders with water that has been used to soak anticoagulant pellets (direct external exposure).  These studies will be conducted at the USDA National Wildlife Research Center in Fort Collins, Colorado, under an IACUC-approved study protocol.

Currently, this study is planned to be conducted mainly with wild-caught Ensatina salamanders (Ensatina eschscholtzii) as a surrogate species for the less common arboreal salamander, with a smaller sample of wild-caught arboreal salamanders for comparison, all captured on the central California mainland.  Salamanders will be captured and shipped to USDA by a separate USFWS contractor.  However, if wild-caught salamanders cannot be provided in a timely manner, the study may be conducted with purchased or provided, captive-reared salamanders (species to be determined) after consultation and agreement between USFWS and USDA.

Reporting: USDA will provide to USFWS a report detailing the study and findings, due December 15, 2016.  The report will include the names and affiliations of all authors, introduction, description of methods, results, discussion, literature cited, acknowledgements, and suggested citation.  The USFWS Interagency Agreement Number will be included on the cover page.

Budget

The budget needed for the study would be $45,000 to fund staff, provide equipment and supplies, support animal care staff and needs, and indirect costs.  Additional funds will be necessary if chemical analyses for rodenticide residues are required.