## Global Timeline
Current Approved Timeline (April 1, 2019, waiver) |  | 2019-04-09 |  | 2019-04-16 | 2019-04-30 |  |  | 2019-05-10 |  | 2019-05-14 |  |  | by Friday before June 7 | 2019-06-07 |  | 2019-07-08 | 2019-07-12 |  | 2019-07-19 | 2019-07-29
Department Review |  |  |  |  | schedule stage 5 |  |  | Stage 5 Briefing to Review Team |  | Exec Sec clearance | [6 empty] | Stage 6 review
briefing submittal |  |  | prepare slideshow |  | submit slideshow to Department |  |  |  |  | note referencing the Review Team clearance and names of attendeees |  |  |  |  | prepare information memorandum |  | submit information memorandum on our decision
Biological Opinion | SOL review | conclude drafting |  |  | BO ready for signature |  |  |  | sign BO, for Exec Sec clearance
share with ECPO, allow 3 weeks
NEPA | [10 empty] | coordinate with EPA filing
final EIS |  |  |  | SOL review complete | submit to Department |  |  |  |  | enter into DTS for ExecSec |  |  | file with EPA
ROD |  |  |  | SOL review complete | submit to Department |  |  |  |  | enter into DTS for ExecSec |  |  | file with EPA | [5 empty] | RO surname routing | signature on ROD
Notice of Availability (NOA) |  |  |  | SOL review complete | submit to Department | RO surname routing |  |  |  | enter into DTS for ExecSec |  | sign NOA | transmit to Federal Register | publication of NOA -- 30-day ROD notice |  | ROD notice closes
ESA section 10
ITP findings | drafting |  |  |  | SOL review complete | coordinate with ECPO | [11 empty] | finalize | RO surname routing | signatures on final decision
Permit instruments | drafting |  |  |  |  | SOL review | coordinate with ECPO |  |  | conclude coordination with ECPO (approx.) | [7 empty] | finalize | RO surname routing | signature on final decision
Tribal Consultations
Formal section 106 consultations | drafting, SOL review, coordination with ECPO | [6 empty] | conclude consultations
Cultural Resources MOU/MOAs | drafting, SOL review, coordination with Corps and ECPO | [6 empty] | have substantive, mature drafts | [9 empty] | sign MOU/MOAs
Sections 7/404 MOU | drafting, SOL review, coordination with Corps and ECPO | [19 empty] | signatures on MOU, follow final decision