## Global Timeline
TASKS - PRODUCTS | STATUS: March 2020 |  |  |  |  | Eastern | Collier Multi- | Species | Habitat | Conservation | Plan
|  | May 11 | June 1 | 2020-06-29 | July 27 | 2020-08-03 |  | 2020-08-17 |  | August 28 |  | September 11 |  | by Friday before October 2 | 2020-10-02 |  | November 2 | November 9 |  | November 16 | November 25
|  | Draft BO submitted by FO |  | NOT under Service or SOL control |  | NOT under Service or SOL control |  |  | Need final HCP before Stage 5 brief, can continue small revisions until decision | [9 empty] | ECPO concurrence before surnaming
Department Review | Stage 5 and subsequent stages to do | [6 empty] | schedule stage 5 |  | Stage 5 Briefing to Review Team |  | Exec Sec clearance | [5 empty] | Stage 6 review
briefing submittal | to do |  | IM and maybe briefing to Department, will need to request schedule waiver |  |  |  | prepare slideshow | submit slideshow to Department |  |  |  | note referencing the Review Team clearance and names of attendeees |  |  |  | prepare information memorandum |  | submit information memorandum on our decision
Department SO 3355 tracking | in pause status, update as needed |  | update DOI database, come off pause | may need to consider pause |  | may need to consider pause | [12 empty] | may need to consider pause
Biological Opinion | draft complete except panther chapter | [8 empty] | BO ready for signature | sign BO, for Exec Sec clearance
|  | RO and FO review and discussion | begin SOL review | begin ECPO review | returned by ECPO
NEPA | [11 empty] | coordinate with EPA filing
final EIS | essentially complete, portions already provided for ECPO's review |  |  | begin SOL review | SOL review complete | begin ECPO review | returned by ECPO | submit to Department | mature draft needed to submit |  |  | enter into DTS for ExecSec |  | file with EPA
ROD | draft started |  |  | begin SOL review | SOL review complete | begin ECPO review | returned by ECPO | submit to Department | mature draft needed to submit |  |  | enter into DTS for ExecSec |  | file with EPA | [5 empty] | RO surname routing | signature on ROD
Notice of Availability (NOA) | to do |  |  | begin SOL review | SOL review complete |  |  | submit to Department | mature draft needed to submit | RO surname routing |  | enter into DTS for ExecSec | sign NOA | transmit to Federal Register | publication of NOA -- 30-day ROD notice |  | ROD notice closes
ESA section 10
ITP findings | drafting started | ongoing drafting |  |  | begin SOL review |  |  |  |  | SOL review complete enough for confidence in legal sufficiency | SOL review needed to begin coordination with ECPO no later than ROD publication | [7 empty] | finalize | RO surname routing | signatures on final decision
Permit instruments | outline of operations drafted | begin drafting |  |  |  |  | begin SOL review |  |  |  | SOL review needed to begin coordination with ECPO no later than ROD publication | [7 empty] | finalize | RO surname routing | signature on final decision
Tribal Consultations | [7 empty] | Alert Tribes to pending decision
Miccosukee | essentially complete | [6 empty] | conclude consultations
Seminoles | formal reply in draft, readying for RO surname | [6 empty] | conclude consultations
Cultural Resources MOU/MOAs | IF NEEDED, not requested by Miccosukee | [6 empty] | IF NEEDED, have substantive, mature drafts | [10 empty] | IF NEEDED, sign MOU/MOAs
Sections 7/404 MOU | draft negotiated between SOL and Corps Counsel, reviewed by ECPO | [20 empty] | signatures on MOU, follow final decision - State Supervisor level