## Not Warranted
SSA R4 Project Plan Timeline Template
|  |  | Task | Duration (Days) | Complete Date | Who | Notes:
SSA Development |  | 1 | Initiation of Project- Rapid Assessment
|  | 2 | KICK-OFF MEETING | 1 | 2017-01-03 | Technical Team, Core Team, and PAO | discuss role and responsibilities of team members, needs, and project plan timeline
|  | 3 | Send Dear Interested Party Letters | 7 | 2017-01-10 | FO
|  | 4 | Biology/Species Needs | 14 | 2017-01-24 | Core Team
|  | 4.1 | Present and Review Biology/Species Needs | 7 | 2017-01-31 | Core Team, Technical Team
|  | 5 | Current Conditions (Habitat and Populations) | 14 | 2017-02-14 | Core Team
|  | 5.1 | Present and Review Current Conditions Analysis | 7 | 2017-02-21 | Core Team, Technical Team
|  | 6 | Future Conditions Analysis | 14 | 2017-03-07 | Core Team
|  | 6.1 | Present and Review Future Conditions | 7 | 2017-03-14 | Core Team, Technical Team
|  | 7 | Write SSA Report | 21 | 2017-04-04 | Core Team
|  | 8 | Review of SSA Report | 7 | 2017-04-11 | Core Team, Technical Team
|  | 9 | Revisions to SSA Report | 7 | 2017-04-18 | FO
|  | 10 | Peer Review | 28 | 2017-05-16 | Peer Reviewers
|  | 11 | Incorporate Peer Review comments | 7 | 2017-05-23 | FO
|  | 12 | Draft SSA to Recommendation Team for Review | 7 | 2017-05-30 | Reccomendation Team
|  | 12.1 | Prepare Briefing Materials for meeting | 7 | 2017-06-06 | Core Team
Decision and SSA Revision |  | 13 | Recommendation Team Meeting | 1 | 2017-11-13 | Core and Reccomendation Teams
|  | 13.1 | Edit SSA Report per Recommendation team | 7 | 2017-11-20 | Core Team
|  | 13.2 | Final Review of SSA Report | 7 | 2017-11-27 | Core Team and RO
|  | 14 | Brief RD Office | 1 | 2017-11-28 | Core Team, RD | Project Manager to schedule with RD
FR Doc Development, Review and Surnaming |  | 15 | Draft Federal Register Document and Species Assessment Form | 7 | 2017-12-04 | Project Manager
|  | 16 | FO and PAO developing outreach package | 7 | 2017-12-11 | FO and PAO | outreach package should be completed by the time SOL reviews FR doc
|  | 17 | Prelim RO review of FR doc | 14 | 2017-12-25 | RO
|  | 17.1 | FO revision | 7 | 2018-01-01 | FO
| RO | 18 | Prelim RSOL and HQ review | 14 | 2018-01-15 | RSOL, HQ
|  |  | FO revision | 1 | 2018-01-16 | FO, RO
|  | 19 | RSOL Formal review | 14 | 2018-01-30 | RSOL
|  | 20 | RO ES Review | 14 | 2018-02-13 | SOL, RO
|  | 21 | FO revision | 7 | 2018-02-20 | FO
| PPM | 22 | RD Review | 14 | 2018-03-06 | RD
|  | 23 | PPM review | 7 | 2018-03-13 | PPM | PPM: Divison of Policy, Performance and Management, internal editors for publication prep
|  | 24 | HQ review | 21 | 2018-04-03 | HQ
|  | 25 | AES/Director/Department | 21 | 2018-04-24 | Project Manager
FR |  | 27 | Send to OFR |  |  |  | Target Date: 5/1/18
|  | 28 | Debriefing Meeting |  |  |  | Discussion on lessons learned and improvements to the process
Formulas:
Complete Date = ([Complete Date, row above]+[Duration (Days)])

## with pCH steps
SSA R4 Project Plan Timeline Template
|  |  | Task | Duration | Start Date | Completion Date | Who | Notes:
SSA Development |  | 1 | Initiation of Project- Rapid Assessment
|  | 2 | KICK-OFF MEETING | 1 day |  |  | Core Team and PAO | discuss role and responsibilities of team members, needs, and project plan timeline
|  | 3 | Send Dear Interested Party Letters | 7 days |  |  | FO
|  | 4 | Biology/Species Needs | 3 weeks |  |  | FO
|  | 4.1 | Present and Review Biology/Species Needs | 1 week |  |  | Core Team | outside species experts?
|  | 5 | Current Conditions (Habitat and Populations) | 3 weeks |  |  | FO
|  | 5.1 | Present and Review Current Conditions Analysis | 1 week |  |  | Core Team | outside species experts?
|  | 6 | Future Conditions Analysis | 3 weeks |  |  | FO
|  | 6.1 | Present and Review Future Conditions | 1 week |  |  | Core Team | outside species experts?
|  | 7 | Write SSA Report | 6 weeks |  |  | FO
|  | 8 | Core Team Review of SSA Report | 1 week |  |  | Core Team | Project Leader Review?
|  | 9 | Revisions to SSA Report | 1 week |  |  | FO
|  | 10 | Peer Review | 5 weeks |  |  | Peer Reviewers | PLs, Reg Liaisons, other internal or partner review?
|  | 11 | Incorporate Peer Review comments | 1 week |  |  | FO
|  | 12 | Draft SSA to Recommendation Team for Review | 10 days |  |  | Rec Team
|  | 12.1 | Prepare Briefing Materials for meeting | 1 week |  |  | Core Team
Decision and SSA Revision |  | 13 | Recommendation Team Meeting | 1 day |  |  | Core and Rec Teams
|  | 13.1 | Edit SSA Report per Recommendation team | 1 week |  |  | Core Team
|  | 13.2 | Final Review of SSA Report | 1 week |  |  | Core Team and RO
|  | 14 | Brief RD Office | 1 day |  |  | Core Team, RD | Project Manager to schedule with RDO
pCH |  | 15 | Start pCH |  |  |  | FO
|  |  | Draft CH Rule and create maps | 4 weeks |  |  | FO
|  | 15.1 | Develop IEM | 2 weeks |  |  | FO
|  | 15.2 | RO Review of IEM | 1 weeks |  |  | PM and Chief of Listing
|  | 15.3 | Draft IEM | 2 weeks |  |  | FO and Partners | Federal Partner Review period
|  | 15.4 | Revised IEM and Screening Tool | 1 week |  |  | FO | Send IEM, Screening tool results, GIS, consultation history, land management plans, Federal Agency coordination responses and public comments to RO
|  | 15.5 | Economic Analysis | 6 weeks |  |  | Contractor
|  | 15.6 | Prepare Revised pCH including economic analysis info | 1 week |  |  | FO
FR Doc Development, Review and Surnaming |  | 16 | Draft Federal Register Document and Species Assessment Form | 1 week |  |  | Project Manager
|  | 16.1 | FO and PAO developing outreach package |  |  |  | FO and PAO | outreach package should be completed by the time SOL reviews FR doc
|  | 16.2 | RSOL review of FR doc and Species Assessment Form | 2 weeks |  |  | ALL | RSOL Review and Surname
| RO | 16.3 | Core Team/RO review of FR doc | 1 week |  |  | Core Team and RO | RO Review and Surname process: PM, Regional Liaison, RSOL, DARD, ARD
|  | 16.4 | Incorporate comments in FR doc | 1 week |  |  | Project Manager
|  | 16.5 | Final review of FR doc by RD | 2 weeks |  |  | SOL, RO | SOL Review and Surname
|  | 16.6 | Final review of FR doc by SOL | 1 week |  |  | RD | RD Review and Surname
| PPM | 16.7 | PPM Review of FR doc | 10 days |  |  | PPM | PPM: Divison of Policy, Performance and Management, internal editors for publication prep
|  | 16.8 | Incorporating PPM comments to FR doc | 1 day |  |  | FO
|  | 16.9 | Deliver SSA and FR doc to ULT manager | 2 weeks |  |  | Regional Liaison | Send to Sarah Quamme and Bridget for review
|  | 16.1 | Brief ULT manager | 1 day |  |  | Project Manager | Brief Sarah Quamme
| HQ | 16.11 | AES/Director/Department | 4 weeks |  |  | Project Manager | Track on DTS
FR |  | 17 | Send to OFR |  |  |  |  | Target Date:
|  | 18 | Debriefing Meeting |  |  |  |  | Discussion on lessons learned and improvements to the process